SENTRAIS

Powered by NOVATE

|  | NFL EVERGAME Phase II Implementation Proposal IT Game Day Compliance & Readiness System |
| --- | --- |

| Document ID | SIPE-NFL-EVERGAME-PROPOSAL-v1.0 |
| --- | --- |
| Classification | NOVATE PROPRIETARY - CLIENT CONFIDENTIAL |
| SIPE Tag | TRANSFORMATION-CHALLENGE-FULL |
| Version | 1.0 ¦ January 2026 |
| Target Start | March 2026 |
| Target Completion | 2026 Preseason Ready (August 2026) |

Prepared for: NFL IT Operations

Prepared by: NOVATE Labs

# Table of Contents

# 1. Executive Summary

## 1.1 Engagement Overview

Following the successful completion of the EVERGAME Proof of Concept, NOVATE is pleased to present this comprehensive implementation proposal for Phase II of the NFL IT Game Day Compliance and Readiness System. This proposal outlines the full implementation journey from Discovery through Operationalization, leveraging the SIPE (Sentrais Innovation Playbook Engine) methodology to ensure forensic rigor, evidence-based decision making, and measurable outcomes.

This engagement is designed as a three-year partnership, ensuring long-term platform evolution and continuous improvement. The Phase II implementation will deliver a production-ready system targeting the 2026 NFL Preseason, with core deliverables including certified Stadium and GDA processes, validated playbooks, and a centralized Game Day Dashboard.

## 1.2 Problem Statement

The NFL currently faces significant operational challenges in managing IT readiness across venues, cities, and league operations:

- Lack of visibility into operational preparedness for critical events

- Reliance on unsecured tools (Google Sheets, WhatsApp) creating security and compliance risks

- Inconsistent reporting leading to delayed issue resolution

- No standardized processes for Stadium Certification or GDA workflows

- Manual coordination bottlenecks preventing continuous optimization

## 1.3 Solution Strategy

NOVATE will implement the EVERGAME platform through the proven NIN (N-Ovate Innovation Nexus) 5D methodology, unifying, standardizing, and analyzing operational data to create a comprehensive readiness ecosystem. The solution encompasses:

| Deliverable | Description |
| --- | --- |
| Centralized System of Record | Unified tracking, reporting, and operational silo elimination through Sentrais platform |
| Game Day Dashboard | Real-time status tracking, prioritization, alerts, and escalation management |
| Enhanced GDA Tools | Streamlined checklists for improved accountability and task tracking |
| Vendor-Supported Framework | Defined structure for vendor collaboration and technology standards |
| Evidence Capture System | Comprehensive audit trail and compliance documentation |
| IT Master Calendar | Integrated scheduling for all IT-related game day activities |
| Stadium Certification | Standardized certification process for all NFL venues |

# 2. Implementation Methodology: The 5D Framework

The NFL EVERGAME Phase II implementation follows the NIN 5D methodology, a proven framework for delivering complex transformation engagements with forensic rigor and measurable outcomes.

## 2.1 Phase Overview

| Phase | Duration | Focus | Key Milestone |
| --- | --- | --- | --- |
| D1: Discover | 3 Weeks | 360 Modeling & Stakeholder Mapping | Problem Validation |
| D2: Diagnose | 4 Weeks | Current State Forensics & Blueprinting | Gap Analysis Complete |
| D3: Design | 5 Weeks | To-Be Process Design & Certification | Process Certification |
| D4: Develop | 8 Weeks | Platform Build & Integration | System Ready |
| D5: Deploy | 4 Weeks | Operationalization & Measurement | Preseason Ready |

## 2.2 Phase 1: DISCOVER (Weeks 1-3)

Purpose: Establish forensic foundation through comprehensive 360 Modeling and stakeholder alignment.

### 360 Modeling Dimensions

| Dimension | Data Collection Focus |
| --- | --- |
| Strategic | NFL IT strategic priorities, league-wide objectives, 3-year roadmap alignment |
| Operational | Current GDA workflows, stadium certification processes, task tracking methods |
| Technical | Existing systems architecture, data flows, integration requirements, security posture |
| Cultural | Change readiness, stakeholder adoption history, training requirements |
| Financial | Budget allocation, ROI expectations, cost optimization opportunities |
| Ecosystem | Vendor relationships, stadium partnerships, third-party dependencies |

### Key Activities

- Executive sponsor interviews and strategic alignment

- Document collection across all 360 dimensions

- Stakeholder mapping with influence/interest matrix

- Problem statement validation with 3+ stakeholder sign-offs

- KPI baseline establishment for success measurement

- Sentrais project initialization and Evidence Ledger activation

### Stage Gate 1 Exit Criteria

- 360 Model Report complete (all 6 dimensions documented)

- Stakeholder Engagement Index (SEI) ≥ 75

- Evidence Quality Rating ≥ 80

- Market research minimum 5 data sources validated

## 2.3 Phase 2: DIAGNOSE (Weeks 4-7)

Purpose: Deep-dive forensics on current state processes, systems, and workflows to establish comprehensive gap analysis.

CRITICAL CHURN ZONE: This phase represents the highest risk period for engagement delays. SIPE churn prevention protocols will be active with enhanced monitoring.

### Current State Analysis

- Stadium Certification Process: Complete audit of existing certification workflows, documentation, and approval chains

- GDA Workflows: Detailed mapping of Game Day Ambassador tasks, checklists, and accountability structures

- Data Architecture: Assessment of current data flows, integration points, and system dependencies

- Evidence Capture Gap: Analysis of current audit trail capabilities vs. requirements

### Key Deliverables

| Deliverable | Description |
| --- | --- |
| Current State Process Maps | Visual documentation of all existing workflows with pain points identified |
| Gap Analysis Report | Comprehensive gap identification between current and required capabilities |
| Risk Register | Prioritized risk assessment with mitigation strategies for HIGH/CRITICAL items |
| Technology Assessment | Technical feasibility analysis with integration requirements |
| Opportunity ROI Matrix | Quantified improvement opportunities with expected ROI |

### Stage Gate 2 Exit Criteria

- Workflow forensics completed with 95%+ accuracy

- All HIGH risks in register have documented mitigation plans

- Scope Stability Score ≥ 85

- Requirements Ambiguity Score ≤ 20

- Executive checkpoint completed with approval to proceed

## 2.4 Phase 3: DESIGN (Weeks 8-12)

Purpose: Create and certify To-Be processes for Stadium Certification, GDA workflows, and 2026 GDA Checklist validation.

### Core Design Workstreams

Workstream 1: Stadium Certification Process Design

- Define standardized certification criteria across all 30+ NFL venues

- Design certification workflow with approval gates and evidence requirements

- Create certification dashboard specifications for real-time status tracking

- Establish recertification cadence and compliance monitoring

Workstream 2: GDA Certification Process Design

- Define GDA competency requirements and certification levels

- Design training curriculum with assessment checkpoints

- Create GDA assignment workflow based on certification status

- Establish ongoing certification maintenance requirements

Workstream 3: 2026 GDA Checklist Playbook

- Design comprehensive game day checklist with task sequencing

- Create escalation protocols with trigger conditions and response SLAs

- Design evidence capture requirements for each checklist item

- Validate playbook with pilot GDA team for usability

### Stage Gate 3 Exit Criteria

- All 3 To-Be processes documented and client-approved

- Technical Feasibility Confidence ≥ 80%

- Stakeholder Alignment Index ≥ 85

- Resource plan validated and committed for Development phase

- Innovation Coefficient ≥ 60 (novel solutions documented)

## 2.5 Phase 4: DEVELOP (Weeks 13-20)

Purpose: Build and integrate the EVERGAME platform components based on certified designs.

### Development Sprints

| Sprint | Duration | Deliverables |
| --- | --- | --- |
| Sprint 1 | Weeks 13-14 | Sentrais Core Configuration, User Management, Authentication |
| Sprint 2 | Weeks 15-16 | Stadium Certification Module, Certification Workflow Engine |
| Sprint 3 | Weeks 17-18 | GDA Tools Module, Checklist Engine, Evidence Capture |
| Sprint 4 | Weeks 19-20 | Game Day Dashboard, Real-Time Monitoring, Alerts/Escalation |

### Platform Components

- Centralized System of Record: Unified data model for all IT readiness tracking

- Game Day Dashboard: Real-time status, alerts, escalation, and executive visibility

- GDA Mobile Tools: Field-ready checklist application with offline capability

- Evidence Capture System: Photo, document, and audit trail management

- IT Master Calendar: Integrated scheduling with dependency management

- Vendor Portal: Third-party access for collaboration and compliance tracking

### Stage Gate 4 Exit Criteria

- All platform components developed and unit tested

- Integration testing complete with <5% critical defects

- User acceptance testing passed by GDA pilot team

- Go/No-Go decision made with evidence-based rationale

- Stage Gate Pass Rate (Development) ≥ 70%

## 2.6 Phase 5: DEPLOY (Weeks 21-24)

Purpose: Operationalize the EVERGAME platform and prepare for 2026 Preseason testing.

### Deployment Activities

- Production environment deployment and security hardening

- GDA team training and certification program execution

- Stadium onboarding with initial certification workflows

- Operational runbook and support documentation delivery

- Preseason dry-run testing and performance optimization

### Preseason Readiness Checklist

| Readiness Item | Target | Owner |
| --- | --- | --- |
| Platform stability (99.9% uptime) | Validated | NOVATE |
| GDA training completion | 100% | NFL IT |
| Stadium certification initiated | 30+ venues | Joint |
| Checklist playbook validated | Complete | NOVATE |
| Executive dashboard operational | Live | NOVATE |
| Support documentation delivered | 100% | NOVATE |
| Dry-run testing complete | 3 events | Joint |

### Stage Gate 5 Exit Criteria

- User adoption ≥ 60% within first 30 days

- Time-to-Value within ±15% of projection

- ROI Realization Rate ≥ 75%

- Client Satisfaction Score ≥ 80

- 2026 Preseason readiness confirmed

# 3. Implementation Timeline

## 3.1 Master Schedule

| Week | Dates | Phase | Key Milestones |
| --- | --- | --- | --- |
| 1-3 | Mar 2-20 | D1: DISCOVER | Kickoff, 360 Modeling, Problem Validation |
| 4-7 | Mar 23-Apr 17 | D2: DIAGNOSE | Current State Forensics, Gap Analysis |
| 8-12 | Apr 20-May 22 | D3: DESIGN | To-Be Process Design & Certification |
| 13-20 | May 25-Jul 17 | D4: DEVELOP | Platform Build & Integration |
| 21-24 | Jul 20-Aug 14 | D5: DEPLOY | Operationalization & Testing |
| 25+ | Aug 17+ | PRESEASON | 2026 Preseason Live Operations |

## 3.2 Critical Path Dependencies

- NFL IT stakeholder availability for interviews (Week 1-3)

- Current state documentation access (Week 4)

- Executive approval for To-Be designs (Week 12)

- GDA pilot team identified for testing (Week 16)

- Stadium access for certification pilot (Week 22)

# 4. Governance & Accountability

## 4.1 Shared Accountability Model

The SIPE methodology enforces shared accountability between NOVATE and NFL IT. The following RACI matrix defines responsibilities:

| Activity | NOVATE | NFL IT |
| --- | --- | --- |
| Project Management & Delivery | R/A | C/I |
| Stakeholder Availability | C | R/A |
| Current State Documentation | C | R/A |
| To-Be Process Design | R/A | C/I |
| Platform Development | R/A | C |
| User Acceptance Testing | C | R/A |
| GDA Training Execution | R/A | C/I |
| Stadium Onboarding | R | A |

R = Responsible | A = Accountable | C = Consulted | I = Informed

## 4.2 Stage Gate Review Process

Each phase concludes with a formal Stage Gate review requiring documented evidence and threshold validation before advancement. No phase progression occurs without:

- Evidence Ledger entries for all exit criteria

- KPI threshold validation (all metrics within acceptable range)

- Executive sponsor sign-off

- Risk assessment review with mitigation plans for any HIGH risks

## 4.3 Communication Cadence

| Meeting | Frequency | Participants |
| --- | --- | --- |
| Project Status | Weekly | NOVATE PM, NFL IT Lead |
| Steering Committee | Bi-weekly | Executive Sponsors, Project Leads |
| Stage Gate Review | Per Phase | All Stakeholders |
| Technical Sync | 2x Weekly | Development Teams |
| Risk Review | Weekly | PM, Risk Owners |

# 5. Risk Management

## 5.1 Key Risk Register

| Risk | Severity | Mitigation Strategy |
| --- | --- | --- |
| Stakeholder availability constraints | HIGH | Schedule interviews 2 weeks in advance; document alternatives for non-available stakeholders |
| Scope expansion during Design | HIGH | Strict change control process; defer non-critical items to Phase III |
| Integration complexity | MEDIUM | Early technical deep-dives; dedicated integration testing sprint |
| GDA adoption resistance | MEDIUM | Champions program; involve GDAs in design phase; demonstrate quick wins |
| Timeline compression | MEDIUM | Buffer built into each phase; prioritized feature list for MVP if needed |

## 5.2 Churn Prevention Protocols

The DIAGNOSE and DESIGN phases (Weeks 4-12) represent the Critical Churn Zone where 60% of engagement delays typically occur. SIPE activates enhanced monitoring:

- Requirements Ambiguity Score tracked daily (Alert if >20, Escalate if >40)

- Stakeholder Alignment Index monitored weekly (Alert if <85)

- Decision Bottleneck Index tracked (Alert if >3 delays, Escalate if >5)

- Executive checkpoint scheduled at Week 7 before Design phase

# 6. Investment Summary

## 6.1 Phase II Implementation Investment

The following investment structure supports the complete 5D implementation through 2026 Preseason readiness. Detailed pricing will be provided in a separate commercial proposal.

| Component | Duration | Investment Type |
| --- | --- | --- |
| D1: DISCOVER Phase | 3 Weeks | Fixed Fee |
| D2: DIAGNOSE Phase | 4 Weeks | Fixed Fee |
| D3: DESIGN Phase | 5 Weeks | Fixed Fee |
| D4: DEVELOP Phase | 8 Weeks | Fixed Fee |
| D5: DEPLOY Phase | 4 Weeks | Fixed Fee |
| Sentrais Platform Licensing | Annual | Subscription |
| Ongoing Support & Evolution | Year 2-3 | Retainer |

## 6.2 Expected ROI

- 30% reduction in game day IT incidents through proactive monitoring

- 50% reduction in issue resolution time through standardized escalation

- 40% efficiency gain in GDA task management through automated workflows

- 100% audit trail compliance for all IT readiness activities

- Elimination of unsecured tool dependency (Google Sheets, WhatsApp)

# 7. Next Steps

## 7.1 Immediate Actions Required

| Week | Action | Owner |
| --- | --- | --- |
| 1 | Review and approve implementation proposal | NFL IT Executive Sponsor |
| 1 | Commercial proposal review and contract negotiation | NFL Procurement + NOVATE |
| 2 | Identify key stakeholders for 360 Modeling interviews | NFL IT Lead |
| 2 | Schedule kickoff meeting for March start | Joint |
| 3 | Contract execution | NFL Legal + NOVATE |
| 3 | Initial document request distribution | NOVATE PM |

## 7.2 Key Contacts

NOVATE Team:

- Executive Sponsor: [To Be Assigned]

- Program Director: [To Be Assigned]

- Engagement Lead: [To Be Assigned]

NFL IT Team (Required):

- Executive Sponsor: [To Be Identified]

- Project Lead: [To Be Identified]

- GDA Program Representative: [To Be Identified]

# Appendix A: SIPE Methodology Reference

The Sentrais Innovation Playbook Engine (SIPE) is NOVATE's intelligence operating system that transforms raw engagement data into predictive insights, automated playbooks, and measurable outcomes. Key components relevant to this engagement:

### Evidence Ledger

Immutable audit trail for all decisions, providing forensic documentation and source-of-truth validation. All engagement activities are logged with timestamps, actors, and rationale.

### Stage Gate System

Structured phase transitions requiring documented evidence and KPI threshold validation. No phase advancement occurs without meeting exit criteria and executive approval.

### 360 Modeling Framework

Comprehensive diagnostic approach examining challenges across six dimensions: Strategic, Operational, Technical, Cultural, Financial, and Ecosystem. Ensures no blind spots in analysis.

### Churn Prevention Intelligence

Predictive monitoring focused on the Diagnose/Design phases where 60% of engagement delays occur. Automated alerts and intervention protocols ensure proactive risk mitigation.

# Document Control

| Document ID | SIPE-NFL-EVERGAME-PROPOSAL-v1.0 |
| --- | --- |
| Version | 1.0 |
| Release Date | January 2026 |
| Classification | NOVATE PROPRIETARY - CLIENT CONFIDENTIAL |
| SIPE Reference | SIPE Core Architecture v1.0 |
| Next Review | Upon Contract Execution |

— END OF DOCUMENT —