Arhasi, Inc. - Novate Labs Inc

GDA Tech Module of Sentrais Frame MVP

Statement of Work

Authors: Chiranjeevi Bhavansikar

Prepared For: Novate Labs Inc

Document Type: Statement of Work (SOW)

Effective Date: Nov 9, 2025

TABLE OF CONTENTS

1. ENGAGEMENT SCOPE	2

2.1 Description of the Scope	2

2.2 In-Scope Activities	2

2.3 Out-of-Scope Activities	3

2.4 Timeline Guidance	3

2. COMMERCIALS	3

2.1 Payment Terms	4

2.2 Ongoing Support	4

2.3 Software Licensing	5

3. ACCEPTANCE CRITERIA	5

4. ASSUMPTIONS	6

4A: PROJECT GOVERNANCE	6

5. RESPONSIBILITIES OF THE CLIENT	7

6. CHANGE MANAGEMENT PROCESS	7

7. AI, DATA USE, AND INTELLECTUAL PROPERTY	8

4. SIGNATURES	9

This Statement of Work is made between Arhasi Inc. (“Service Provider Inc.”), a Texas Incorporation with its principal place of business at 5900 Balcones Dr, Suite 100, Austin, TX 78731 (‘Service Provider”) and Novate Labs LLC. (“Client”), with its principal place of business at ____________________________________ (“Client”) and is effective as of the date of execution by the last party indicated on the signature page herein (“Effective Date”). This document is a SOW accepted under the terms and conditions agreed upon by both parties in the Professional Services Agreement.

The client would like to employ Service Provider Inc. 's services and technical resources to perform development of this POC (“Project”) and implement into the client’s AWS Cloud environment.

Service Provider Inc. will execute the Project for an estimated 2,280 hours, expected to be completed over 13 weeks, starting on Nov 10, 2025. The estimated duration of the Services is subject to change based on the scope of work, resources allocated, and any modifications, additions, or specific requests made by the Client. The Service Provider will provide weekly reports detailing hours consumed in the execution of the Services.

# 1. ENGAGEMENT SCOPE

## 2.1 Description of the Scope

Service Provider will develop MVP for the GDA Tech Module of the Sentrais Frame to demonstrate the following Game Ops features, specifically related to the event type “NFL Game”:

- Dynamic Mapping and Auto Assign

- Admin Dashboards

- Mobile Friendly UX/UI

- Authentication and Authorization with Okta and GMS API

- System Management Features

## 2.2 In-Scope Activities

Service Provider Inc. considers the following activities to be “in-scope” in order to complement the above objectives:

- Develop GDA Tech Module in Python that is deployable on AWS Services with specific emphasis on the functionality outlined above

- Develop NFL GDA Tech Module front-end web portal pertaining to the functionality outlined above based on the UX designs provided by the Client by mid November, 2025

- Develop user access control model

- Develop a logical data model and implement a physical data model on AWS Services based on the representative data provided by the Client

- Deployment into NFL Innovation AWS Sandbox

- Unit Testing and Integration Testing

- User Enablement and Feedback

- Engagement and Adoption Cycle

## 2.3 Out-of-Scope Activities

Service Provider Inc. considers the following activities to be “out-of-scope”:

- Development of UX designs

- Mobile App development

- Encrypted Communications Integration

- Operationalization of the Module and any requirements outside the scope of GDA Tech Module

- Documentation

## 2.4 Timeline Guidance

- Development and Deployment: Nov 10, 2025 - Jan 9, 2026

- User Enablement and Feedback: Jan 12, 2026 - Feb 10, 2026

Documentation & SOPs (required for acceptance): Provider will allude to these guidelines to deliver

an architecture package (context/component/sequence diagrams; AWS services and IaC), data artifacts

(logical + physical models, dictionary, sample datasets), runbooks/SOPs (deployment, rollback, on-call,

incident, access provisioning, backup/restore), security memos (threat model, IAM proposals, key

management, secrets handling), admin/operator guide, and recorded handover session(s) with slides and

user guide for production build and will adopt the best effort approach for the MVP.

# 2. COMMERCIALS

The Services will be billed on a Time & Materials basis at the rates specified in this SOW. For budgeting purposes, the estimated cost for up to the 2,280 hours of Services is $285,000 USD. Actual fees will be based on the hours expended and materials used.

Start Gate / NTE: Services shall be performed on a Time & Materials basis with a Not-To-Exceed (NTE) cap of 2,280 hours (“Initial NTE”). Provider shall not exceed the NTE without Client’s prior written approval via Change Order.

Pre-Authorization: All billable work must map to a Client JIRA ticket in Approved status with Estimate,

Assignee, Target Sprint, and named Client Approver. Time logged without this status is non-billable.

Non-Billable: Non-billable categories include: (i) rework to remediate Sev-1/2 defects introduced by

Provider, (ii) duplicate effort due to Provider error, (iii) Provider ramp/learning unrelated to Client stack,

(iv) corrections where deliverables failed agreed tests, and (v) unapproved scope exploration/spikes.

Weekly Burn Controls: Weekly, Provider will supply: (a) timesheet export at ticket granularity, (b)

burn-up vs. NTE, (c) ETC/forecast to complete, (d) variance commentary, and (e) risk/issue log with

owners and due dates.

Hours Freeze: If forecast shows >90% NTE utilization without all P0 scope accepted, Provider will

pause new work (except Sev-1/2 fixes) pending Client decision on scope tradeoffs or NTE increase.

Expenses: Expenses will be reimbursed only if pre-approved in writing and subject to caps.

Travel & Expenses: Travel and expenses require Client’s prior written approval and a monthly cap of

$5000. Travel is considered approved provided there is an onsite agenda.

## 2.1 Payment Terms

Invoicing and Payment:  Payment shall be due within thirty (30) days of receipt of the invoice by the Client, Client. 50% net 30 is due upon signature of this agreement, 50% due upon Client’s acceptance of the implementation.

The Service Provider shall retain all rights, title, and interest in the Deliverables and any associated Intellectual Property until such time as the Client has made full payment of all amounts due under this SOW. Transfer of Deliverables and assignment of Intellectual Property rights to the Client shall occur only upon receipt of such full payment.

The Client shall pay Service Provider within 30 days of receipt, and Service Provider withholds the right to refuse service to the Client should this period be exceeded. Invoices will be issued to Client on the last day of the month for the work executed each month. Undisputed payments due beyond 60 days from the invoice date will be referred to collections and/or credit agencies and will be subject to 2% interest per month outstanding.

## 2.2 Ongoing Support

The Service Provider will provide Product-Level Fixes, Performance Re-Engineering, Escalations post Feb 10, 2026. The cost of $6000 per month for this support billed monthly will include 50 hours of support available each month with industry defined Priority SLA Support.

## 2.3 Software Licensing

The Service Provider may use its proprietary AI-Powered Dashboard technology with Conversational Analytics (AI.Insights, also known as TrustIQ) in the deliverables. In case, this proprietary technology is used, then there is an annual license fee of $36,000 per annum. There is no restriction on the number of users and data sources for the NFL GDA use case. The Service Provider will make this available at no additional cost to the Client for the first 6 months, a value of $18,000. A separate licensing and subscription agreement will be provided to the Client provided the technology is leveraged in the delivery of services.

# 3. ACCEPTANCE CRITERIA

Upon completion of the implementation and fulfillment of the requirements specified in this document, Service Provider Inc. will provide the solution artifacts and any relevant documentation to the Client.  Client to review and confirm the completion of this Project in writing via email.

By signing below, the Client agrees to engage with Service Provider Inc., the Service Provider, to be contractually obliged to deliver the Services specified in this Statement of Work to the Client.

Acceptance Criteria: Service Provider Inc. will hand over all the artifacts developed during the course of this Project to the Client. The Client will review the artifacts based on the predefined and agreed Acceptance Criteria:

- The functional MVP web interface and behavior aligns with the designs and requirements defined provided by the Client by mid November, 2025

Test Evidence & Environments: Provider will deliver a test plan, test cases mapped to each Acceptance Criterion, and UAT scripts for any production build. Builds will be demonstrated in the Client staging environment mirroring production topology, with CI/CD pipeline evidence of repeatable deployment. The acceptance criteria will be provided by the Client and UAT will be performed by the client.

Non-Functional Requirements (NFRs): Non-functional acceptance will be measured only against the mutually agreed NFR targets and test methods documented in Attachment A, as approved in SteerCo for any production build. Illustrative baselines are not acceptance criteria.

Review and Feedback: The Client will have twenty (20) business days after complete delivery of code, documentation, test evidence, and the UAT package to review and provide written feedback.

Auto-Acceptance: Deliverables will be deemed accepted if no feedback is provided within the review period, except where:

● any Sev-1/2 defects exist,

● agreed NFR targets (Attachment A) are unmet, or

● required test evidence/documentation is incomplete.

Defect Thresholds: Final acceptance requires zero Sev-1/2 defects and no more than three (3) Sev-3 defects with mutually agreed remediation dates.

Warranty: The Provider warrants deliverables for ninety (90) days post-acceptance and will remediate Provider-attributable defects at no charge (Sev-1 within one business day; Sev-2 within three business days).

# 4. ASSUMPTIONS

- All development/deployment will be performed in the NFL AWS sandbox environment.

- Knowledge transfer of the Project deliverables developed will be provided to Service Provider Inc. by The Client.

- The Client ensures the AWS environment with all necessary prerequisites to develop and deploy the solution is available on time.

- Configuration is limited to a single AWS project and VPC, specifically the Sandbox environment

- The Client is responsible for making all the required data available to be populated into the UX/UI.

- Access to necessary APIs, tools, applications and environments.

- No non-standard performance optimizations.

- The Client provides the required configuration of infrastructure and networking and security services on AWS to enable deployment.

- No security and networking configurations will be performed by the Service Provider.

- Any configurations required that are outside the purview of AWS will be performed by the Client.

- No FedRamp or any other regulatory certification is warranted or provided by the Service Provider.

- The Client is available at the requested dates for domain knowledge sharing and any other technical assistance.

- All services will be performed in a non-production environment.

- The Client will provide a Virtual Desktop or secured desktop environment and appropriately secure  and control access to its AWS resources for Service Provider to protect The Client’s confidential information.

- Service Provider may use a preferred and optimal set of AWS services, open source technologies and its own proprietary R.A.P.I.D hosted service to accelerate and enhance the experience of the deliverables.

- The services will be delivered through a combination of onshore and offshore resources.

- The Service Provider may use the name of the client and refer to the performance of the services without disclosing any confidential information, in marketing and publicity materials, as an indication of its experience. References to either Party B’s Clients such as NFL will only be referenced upon a written agreement from the client.

# 4A: PROJECT GOVERNANCE

● SteerCo: A weekly 45-minute SteerCo meeting will be held, with a 24-hour pre-read shared in

advance. The pre-read will include project status, KPIs, burn vs. NTE, and a summary of risks

and issues.

● RACI: Attachment B defines the RACI matrix across Architecture, Security, Data, DevOps,

QA/UAT, and Release. The Provider may not reassign Key Personnel without the Client’s prior

written approval.

● Change SLAs: For any scope or estimate requests, the Provider will respond within two (2)

business days with options and impact assessments. No work may begin without written approval

from the Client.

● NFR Alignment: The parties will complete the NFR Alignment Workshop within the first five

(5) business days of the project start. Final agreed-upon targets and test methods will be

documented in Attachment A. Any subsequent changes to NFRs require a formal Change Order.

# 5. RESPONSIBILITIES OF THE CLIENT

- System and Data Access: Providing Service Provider Inc. access to relevant data sources and systems to the existing AWS Cloud environment. This might involve granting access to confidential databases, APIs, or other data repositories.

- Domain Knowledge Transfer: Sharing domain expertise, business rules, and contextual information necessary for understanding the architecture and defining appropriate acceptance criteria for the implementation.

- Feedback and Validation: Actively participating in Project validation and providing feedback on the deployments. This could include but not be limited to reviewing configurations, evaluating dataflow, and providing insights based on the architecture.

- Resource Allocation: Allocating necessary resources within the organization, such as personnel, infrastructure and budget, to support the execution of the implementation.

- Stakeholder Engagement: Facilitating communication and co-ordination between relevant stakeholders within the organization.

- Compliance and Legal Considerations: Ensuring compliance with relevant regulatory requirements, data privacy laws, and contractual obligations. This might involve providing legal clearance for data usage and ensuring that the deployment meets industry-specific standards.

- Access to Subject Matter Experts: Providing access to subject matter experts who can offer insights into the architecture, assist in configurations, and guide decision-making throughout the process.

- Commitment to Success: Demonstrating a commitment to the success of the engagement by actively engaging in the process, addressing challenges promptly, and aligning organizational goals with the objectives of the implementation.

# 6. CHANGE MANAGEMENT PROCESS

- Identification of Change: Any party involved in the Project can identify a change that may be required in the SOW. This could be due to shifts in project requirements, scope adjustments, regulatory changes, or other unforeseen circumstances.

- Change Request Submission: The party proposing the change submits a formal written change request outlining the details of the proposed modification. This request typically includes information such as the reason for the change, the impact on project scope, timeline, budget, and any additional resources required.

- Review and Evaluation: The proposed change is reviewed and evaluated within 14 days by both parties, including project managers, stakeholders, and subject matter experts. They assess the feasibility, implications, and potential risks associated with implementing the change.

- Impact Assessment: The impact of the proposed change on the project is assessed in terms of timeline, budget, resources, and deliverables. This assessment helps in understanding the implications of the change and determining whether it aligns with the project objectives.

- Negotiation and Agreement: If the change is deemed necessary and feasible by both parties, negotiations are to take place between Service Provider Inc. and the Client to reach an agreement on the revised terms with such review to be completed within fourteen (14) days. This negotiation may involve discussions on adjustments to project scope, timeline extensions, additional budget allocations, updating relevant documentation or other relevant terms.

- Documentation of Changes:  If an agreement is reached, the changes to the SOW are documented in writing, typically through an amendment or addendum to the original SOW document. This document outlines the revised scope, timeline, budget, and any other pertinent details related to the change.

- Approval and Sign-off: Both parties review and approve the amended SOW document without any unreasonable delay, acknowledging their acceptance of the proposed changes and their commitment to implementing them. This sign-off ensures that all stakeholders are in agreement with the revised terms and conditions.

- Implementation of Changes: With the amended SOW in place, both parties proceed to implement the approved changes according to the agreed-upon timeline and specifications. This may involve adjusting project plans, allocating resources, and updating relevant documentation.

- Monitoring and Control: Throughout the remainder of the Project, on-going monitoring and control mechanisms are put in place to track progress, assess the impact of the changes, and address any issues or deviations that may arise. This helps in ensuring that the Project stays on track and that the revised objectives are met effectively.

# 7. AI, DATA USE, AND INTELLECTUAL PROPERTY

● Data Use: The Provider shall not train, fine-tune, or otherwise use any Client data, metadata,

prompts, or outputs to develop or improve models or services beyond the scope of this

engagement.

● Artifacts & Intellectual Property: The terms in the PSA are applicable.

● Third-Party Models/Services: The terms in the PSA are applicable.

8. SECURITY, COMPLIANCE, AND OFFSHORE CONTROLS

● All Provider personnel with access to Client systems or data must complete background screening

and relevant security training.

● Offshore access to Client data or systems requires prior written approval from the Client, full

disclosure of the country where access will occur, and mandatory use of VPN and Multi-Factor

Authentication (MFA).

● No Client data shall be stored or accessed on personal devices. All data must be encrypted in

transit and at rest. Secrets and credentials must be managed in accordance with Client security

standards.

● The Client reserves the right to audit Provider access logs, timesheets supporting invoices, and

compliance with this Section, upon reasonable advance notice.

9. KEY PERSONNEL & SUBCONTRACTING

● Key Personnel: The following individuals are designated as Key Personnel for this engagement:

Chiru Bhavansikar, Hari Jayaraman, Mary Nikitha Kasipati and Jeenal Mehta. Any replacement

of Key Personnel requires the Client’s prior written approval.

● Subcontracting: The Provider may subcontract portions of the work with prior Client approval but

remains fully responsible and liable for the performance and compliance of all subcontractors.

10. TERMINATION, LIABILITY, AND INDEMNITY

● The terms in the PSA are applicable

# 4. SIGNATURES

Service Provider: Arhasi Inc.

Signature: ___________________________

Printed Name: ________________________

Title: _____________________

Date: ______________

Client: Novate Labs LLC.

Signature: ____________________________

Printed Name: _________________________

Title: _____________________

Date: ______________