EVERGAME 360

Temporal Playbook Mapping

NFL Game Day Operations Platform

Validation Test Document | 1/4/2026

# Executive Summary

EVERGAME 360 transforms static NFL game day checklists into dynamic, temporally-orchestrated playbooks. Each system has embedded SLAs unique to its operational requirements, all synchronized to kickoff time. GDAs assigned to each position will select their location and see only their mapped tasks with real-time compliance tracking.

| System | Hat Color | Qty | Positions |
| --- | --- | --- | --- |
| IVRS | Blue | 4 | Home Booth, Visitor Booth, Home Field, Visitor Field |
| SVS | Purple | 4 | Home Booth, Visitor Booth, Home Sideline, Visitor Sideline |
| C2P | Orange | 2 | Home, Visitor |
| FTR | Gray | 1 | N/A |
| IR Tech | Gray | 1 | N/A |
| O2O | Gray | 1 | N/A |
| Hawk-Eye | Vendor | 1 | N/A |
| WiFi | Blue | 1 | N/A |
| EFC | Orange-EFC | 1 | N/A |

# Temporal Frame Overview

The EVERGAME 360 temporal framework maps all game day tasks to six unified milestones (M0-M6), with M0 representing GD-1 (day before game) activities. All times are relative to kickoff.

| Frame | Milestone | Timing | Description |
| --- | --- | --- | --- |
| M0 | Milestone 0: GD-1 | T-1 Day | Day Before Game - Pre-Setup & Preparation |
| M1 | Milestone 1: Pre-Game Prep | T-7 to T-5 Hours | Pre-Game Preparation & Testing |
| M2 | Milestone 2: Operational Confirm | T-5 to T-4 Hours | Operational System Confirmation |
| M3 | Milestone 3: Inspections | T-4 to T-3 Hours | Inspections & Pre-Game Technology Check |
| M4 | Milestone 4: Broadcast Ready | T-3 to Kickoff | Broadcast & Technician Readiness |
| M5 | Milestone 5: Live Monitoring | During Game | Live Monitoring & Real-Time Adjustments |
| M6 | Milestone 6: Post-Game | End of Game | Post-Game Equity Review & Departure |

## Task Distribution by Frame

| Frame | Task Count | Systems Active |
| --- | --- | --- |
| M0 | 81 | Hawk-Eye-GD1 |
| M1 | 8 | Hawk-Eye, WiFi, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |
| M2 | 167 | IVRS, FTR, IR Tech, O2O, Hawk-Eye, WiFi, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |
| M3 | 124 | FTR, IR Tech, O2O, Hawk-Eye, WiFi, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |
| M4 | 69 | IVRS, IR Tech, O2O, Hawk-Eye, WiFi, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |
| M5 | 14 | Hawk-Eye, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |
| M6 | 102 | IVRS, FTR, IR Tech, O2O, Hawk-Eye, WiFi, C2P-Home, C2P-Visitor, SVS-Home, SVS-Visitor, EFC |

# Milestone 0: GD-1

Timing: T-1 Day | Day Before Game - Pre-Setup & Preparation

## Hawk-Eye-GD1

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-GD1-1.0 | Arrival and TV Truck Contact | - | 0 min |
| Hawk-Eye-GD1-1.0 | Clock in on the UKG App | - | 0 min |
| Hawk-Eye-GD1-1.1 | Review WhatsApp groups for any game-specific details, camera plan, patch list | - | 0 min |
| Hawk-Eye-GD1-1.2 | Post 'Hawk-Eye on-site' in the both the Football Technology and Hawk-Eye Support WhatsApp groups | - | 0 min |
| Hawk-Eye-GD1-1.3 | Establish contact with: -- TRUCK COMPOUND Technical Manager (sync test) EIC/Engineers-in-Charge (feeds/patching) V1 (feeds/patching) | - | 0 min |
| Hawk-Eye-GD1-1.4 | Confirm house camera locations (if any and if not already known) with the tech manager, and share in the Hawk-Eye Support WhatsApp group | - | 0 min |
| Hawk-Eye-GD1-1.5 | Confirm access to: Truck Dock/IO Panel, FTC Rack Room, IVR Booth, Instant Replay Booth | - | 0 min |
| Hawk-Eye-GD1-2.0 | FTC Rack Room / Hawk-Eye Rack | Hawk-Eye GD-1 (1.0-1.5) | 0 min |
| Hawk-Eye-GD1-2.1 | Confirm both PDUs are powered | - | 0 min |
| Hawk-Eye-GD1-2.2 | Confirm UPS is fully charged | - | 0 min |
| Hawk-Eye-GD1-2.3 | Only if asked by AMGC, login to KVM | - | 0 min |
| Hawk-Eye-GD1-2.4 | Only if asked, use KVM to login to capture servers | - | 0 min |
| Hawk-Eye-GD1-2.5 | Only if asked, relaunch SMARTRemoteServer | - | 0 min |
| Hawk-Eye-GD1-2.6 | A/C Unit Stadiums Only: Confirm fan and compressor are powered and operating as expected | - | 0 min |
| Hawk-Eye-GD1-2.7 | A/C Unit Stadiums Only: Verify drainage is working as expected, check for leaking or water | - | 0 min |
| Hawk-Eye-GD1-2.8 | A/C Unit Stadiums Only: Check and clean filters as needed | - | 0 min |
| Hawk-Eye-GD1-3.0 | Patching | - | 0 min |
| Hawk-Eye-GD1-3.0 | For A-Games using flyaway extensions, see green checklist at the bottom | Hawk-Eye GD-1 (2.1-2.8) | 0 min |
| Hawk-Eye-GD1-3.1 | Run looms safely between TV truck and I/O panel | Hawk-Eye GD-1 (8.1-8.7) | 0 min |
| Hawk-Eye-GD1-3.2 | Confirm patch list with EIC/V1, share any changes with Hawk-Eye Support WhatsApp group | - | 0 min |
| Hawk-Eye-GD1-3.3 | Patch looms into I/O patch panel according to Hawk-Eye patch list | - | 0 min |
| Hawk-Eye-GD1-3.4 | Confirm what time we should expect feeds and share with Hawk-Eye Support WhatsApp group | - | 0 min |
| Hawk-Eye-GD1-4.0 | IR (Instant Replay) Set-Up | Hawk-Eye GD-1 (3.1-3.4) | 0 min |
| Hawk-Eye-GD1-4.0 | If not already on, power the IR rack through the UPS | - | 0 min |
| Hawk-Eye-GD1-4.1 | If it does not power on automatically, power on remote viewer (RSV/V2) | - | 0 min |
| Hawk-Eye-GD1-4.2 | If it does not power on automatically, power on replay booth viewer (RBV/V1) | - | 0 min |
| Hawk-Eye-GD1-4.3 | Ensure 3x USB's are plugged into the replay booth viewer (RBV/V1) | - | 0 min |
| Hawk-Eye-GD1-4.4 | Log-in to replay booth viewer (RBV/V1) | - | 0 min |
| Hawk-Eye-GD1-4.5 | Check touchscreen functionality on all three monitors | - | 0 min |
| Hawk-Eye-GD1-4.6 | Inform Support that Instant Replay is Ready for Launch! | - | 0 min |
| Hawk-Eye-GD1-4.7 | Take a photo of the fully setup Instant Replay booth and post it in the Hawk-Eye WhatsApp | - | 0 min |
| Hawk-Eye-GD1-5.0 | IVR (Injury Video Review) Booth Setup | Hawk-Eye GD-1 (4.0-4.7) | 0 min |
| Hawk-Eye-GD1-5.1 | setup Home AIO (All-in-One PC) - PC power - decimator - decimator power - HDMI from PC to decimator 'HDMI Input' - BNC/coax from decimator to Home IVR wall port - ethernet from PC to Home IVR wall por | - | 0 min |
| Hawk-Eye-GD1-5.2 | setup Home Spotter 24" Dell Monitor - monitor power - decimator - decimator power - BNC/coax from Home wall port to decimator - HDMI from decimator to monitor - stream deck mini - touchscreen USB into | - | 0 min |
| Hawk-Eye-GD1-5.3 | Power on & log-in to Home AIO | - | 0 min |
| Hawk-Eye-GD1-5.4 | Confirm Home Spotter is receiving input from Home AIO (blue IVRS background 'Home Sideline') AND Check touchscreen functionality on Home AIO AND Home Spotter | - | 0 min |
| Hawk-Eye-GD1-5.5 | Confirm both Home stream decks are programmed | - | 0 min |
| Hawk-Eye-GD1-5.6 | setup Visitor AIO (All-in-One PC) - PC power - decimator - decimator power - HDMI from PC to decimator 'HDMI Input' - BNC/coax from decimator to Visitor IVR wall port - ethernet from PC to Visitor IVR | - | 0 min |
| Hawk-Eye-GD1-5.7 | setup Visitor Spotter 24" Dell Monitor - monitor power - decimator - decimator power - BNC/coax from Visit wall port to decimator - HDMI from decimator to monitor - stream deck mini - touchscreen USB | - | 0 min |
| Hawk-Eye-GD1-5.8 | Power on & log-in to Visitor AIO | - | 0 min |
| Hawk-Eye-GD1-5.9 | Confirm Visitor Spotter is receiving input from Visitor AIO (blue background saying 'Visit Sideline') AND Check touchscreen functionality on Visitor AIO AND Visitor Spotter | - | 0 min |
| Hawk-Eye-GD1-5.1 | Confirm both Visitor stream decks are programmed | - | 0 min |
| Hawk-Eye-GD1-5.11 | setup UNC AIO (All-in-One PC) - power - ethernet from wall to PC - keyboard - mouse - stream deck XL - Xbox controller | - | 0 min |
| Hawk-Eye-GD1-5.13 | Power on & log-in to UNC AIO | - | 0 min |
| Hawk-Eye-GD1-5.14 | Confirm UNC stream deck is programmed | - | 0 min |
| Hawk-Eye-GD1-5.15 | Inform Support that IVR Is Ready for Launch! | - | 0 min |
| Hawk-Eye-GD1-5.16 | Take a photo of the fully setup IVR booth and post it in the Hawk-Eye WhatsApp | - | 0 min |
| Hawk-Eye-GD1-6.0 | Testing & Confirmation | Hawk-Eye GD-1 (5.1-5.16) | 0 min |
| Hawk-Eye-GD1-6.1 | Fax all camera feeds to confirm they are correct according to our patch list, using UNC Viewer (CTRL+ALT+P) or Blackmagic monitor. Some cameras may not be up until GD (eg house cameras and All22). I | - | 0 min |
| Hawk-Eye-GD1-6.2 | Troubleshoot missing feeds with TV -- Best practice is to bring all of our needs to the truck at one time, including confirming that we should be expecting colour bars/grey/black on the angles we see | - | 0 min |
| Hawk-Eye-GD1-6.3 | Verify RSV and RBV at the VJF in the Hawk-Eye Rack | - | 0 min |
| Hawk-Eye-GD1-6.4 | Verify UTH A can toggle between RBV (from Replay Booth Viewer) and RSV (from AMGC/Remote Viewer) | - | 0 min |
| Hawk-Eye-GD1-6.5 | Verify UTH B can toggle between RBV (from Replay Booth Viewer) and RSV (from AMGC/Remote Viewer) | - | 0 min |
| Hawk-Eye-GD1-6.6 | Verify LTG A and LTG B at the VJF in the Hawk-Eye Rack | - | 0 min |
| Hawk-Eye-GD1-6.7 | Verify that PGM A and PGM B are correct and identical | - | 0 min |
| Hawk-Eye-GD1-6.8 | Verify PGM A and PGM B have audio | Hawk-Eye GD-1 (6.1-6.7) | 0 min |
| Hawk-Eye-GD1-6.1 | Post photos of World Feed A and B on a test monitor at the truck dock IO to the NFL World Feed / Hawk-Eye WhatsApp channel | Hawk-Eye GD-1 (6.8 & 7.0-7.6) | 0 min |
| Hawk-Eye-GD1-6.11 | Set IVRS Layouts (see purple checklist at the bottom) | - | 0 min |
| Hawk-Eye-GD1-6.12 | Confirm with support that they are happy with the status of the IR and IVRS booths AND line to gain & replay cameras | - | 0 min |
| Hawk-Eye-GD1-6.13 | Verify with the AMGC if any Leikr watch updates are required, if yes then plug watches into RSV (bottom) IR machine | - | 0 min |
| Hawk-Eye-GD1-6.14 | Secure Xbox controllers from IR and IVRS for the night | - | 0 min |
| Hawk-Eye-GD1-6.15 | Leave all PCs and monitors powered on | - | 0 min |
| Hawk-Eye-GD1-6.16 | Reconfirm sync time with the Tech Manager and post in the Hawk-Eye WhatsApp group | - | 0 min |
| Hawk-Eye-GD1-6.17 | Inform Football Technology and Hawk-Eye WhatsApp groups when leaving site -- 'Hawk-Eye off site' | - | 0 min |
| Hawk-Eye-GD1-6.18 | Clock out on the UKG App | - | 0 min |
| Hawk-Eye-GD1-7.0 | IVRS Layouts | Hawk-Eye GD-1 (6.1-6.7) | 0 min |
| Hawk-Eye-GD1-7.0 | Inform Support that you are beginning to build layouts, and request support or guidance as needed | - | 0 min |
| Hawk-Eye-GD1-7.1 | Set Home Layouts F1 = Left of Field Layout F2 = Center Layout F3 = Right of Field Layout ALL = All Layout Monitor 1 of 2 = Maximum of 20 angles, Center tile is Output 1 Monitor 2 of 2 = SINGLE fully | - | 0 min |
| Hawk-Eye-GD1-7.2 | Set Visitor Layouts F1 = Left of Field Layout F2 = Center Layout F3 = Right of Field Layout ALL = All Layout Monitor 1 of 2 = Maximum of 20 angles, Center tile is Output 1 Monitor 2 of 2 = SINGLE fu | - | 0 min |
| Hawk-Eye-GD1-7.3 | Set UNC Layouts F1 = Left of Field Layout F2 = Center Layout F3 = Right of Field Layout ALL = All Layout Monitor 1 of 1 = Maximum of 20 angles, Center tile is Output 1 EXCEPT ALL LAYOUT Monitor 1 o | - | 0 min |
| Hawk-Eye-GD1-7.4 | Double check that Monitor 2 of 2 for the 'ALL' layout on Home and Visitor is set to SINGLE fully SCREEN, Broadcast Live | - | 0 min |
| Hawk-Eye-GD1-7.5 | Double check that layouts for Home, Visitor and UNC are identical | - | 0 min |
| Hawk-Eye-GD1-7.6 | Inform Support that IVR Layouts are complete and ready to be verified! | - | 0 min |
| Hawk-Eye-GD1-8.0 | Flyaway Rack (A Game Only) | Hawk-Eye GD-1 (3.0) | 0 min |
| Hawk-Eye-GD1-8.1 | Locate flyaway rack from TV truck, at loading dock or from stadium contact | - | 0 min |
| Hawk-Eye-GD1-8.2 | Move flyaway rack to Truck I/O | - | 0 min |
| Hawk-Eye-GD1-8.3 | Position flyaway rack in proximity to: - NEMA 5-20R power source - I/O patch panel for fibre connection and patching | - | 0 min |
| Hawk-Eye-GD1-8.4 | Plug in 2x flyaway rack PDUs (power distribution unit) into NEMA 5-20R power sources | - | 0 min |
| Hawk-Eye-GD1-8.5 | Plug in 2x Opticalcon cables between I/O patch panel and flyaway rack panel | - | 0 min |
| Hawk-Eye-GD1-8.6 | Patch looms into flyaway rack patch panel according to patch list | - | 0 min |
| Hawk-Eye-GD1-8.7 | Coordinate with support to confirm flyaway rack is network connected and feeds are correct | - | 0 min |

# Milestone 1: Pre-Game Prep

Timing: T-7 to T-5 Hours | Pre-Game Preparation & Testing

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-2.1 | Provide helmet modules to equipment mgr | C2P Home (1.1-1.16) | -300 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-2.1 | Provide helmet modules to equipment mgr | C2P Visitor (1.1-1.16) | -300 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-1.1 | Clock into UKG upon arrival to the stadium and post 'EFCs on-site' in the Football Technology WhatsApp group | - | -300 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-1 | Arrival | Hawk-Eye GD-1 (ALL) | -420 min |
| Hawk-Eye-2 | Sync Test | Hawk-Eye (1.0-1.8) | -360 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-6.1 | Ensure video signals for Hi50 and HiEZ are crisp and there's no flickering | SVS Home (5.1-5.6) | -300 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-6.1 | Ensure video signals for Hi50 and HiEZ are crisp and there's no flickering | SVS Visitor (5.1-5.6) | -300 min |

## WiFi

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| WiFi-4.1 | Conduct Home WiFi test using Insider tool to ensure channels in use are clean. | WiFi (3.1) | -300 min |

# Milestone 2: Operational Confirm

Timing: T-5 to T-4 Hours | Operational System Confirmation

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-1.1 | Post 'C2P on-site' in the Football Technology WhatsApp group | EFC (2.1-2.5) | -240 min |
| C2P-Home-1.2 | Pick up field access armband | - | -240 min |
| C2P-Home-1.3 | Mount antennas on tech cart | - | -240 min |
| C2P-Home-1.4 | Turn on UPS and FS2 | - | -240 min |
| C2P-Home-1.5 | Attach repeater antenna to SCC cart | - | -240 min |
| C2P-Home-1.6 | Charge all HT batteries | - | -240 min |
| C2P-Home-1.7 | Test all 5 Offense helmet modules on FS2 (Simplex and Duplex) | - | -240 min |
| C2P-Home-1.8 | Test all 5 Defense helmet modules on FS2 (Simplex and Duplex) | - | -240 min |
| C2P-Home-1.9 | Test both Local cutoff switches on FS2 | - | -240 min |
| C2P-Home-1.1 | Switch power and RF to "FS1" position | - | -240 min |
| C2P-Home-1.11 | Test all 5 Offense helmet modules on FS1 (Simplex and Duplex) | - | -240 min |
| C2P-Home-1.12 | Test all 5 Defense helmet modules on FS1 (Simplex and Duplex) | - | -240 min |
| C2P-Home-1.13 | 10 helmet modules are ready for pickup by equipment manager at 3.5 hours | - | -240 min |
| C2P-Home-1.14 | Confirm both power cables are connected to line power | - | -240 min |
| C2P-Home-1.15 | Test one Local Cutoff switch on FS1 repeater. | - | -240 min |
| C2P-Home-1.16 | Test offense power level to far right endline | - | -240 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-1.1 | Post 'C2P on-site' in the Football Technology WhatsApp group | EFC (2.1-2.5) | -240 min |
| C2P-Visitor-1.2 | Pick up field access armband | - | -240 min |
| C2P-Visitor-1.3 | Mount antennas on tech cart | - | -240 min |
| C2P-Visitor-1.4 | Turn on UPS and FS2 | - | -240 min |
| C2P-Visitor-1.5 | Attach repeater antenna to SCC cart | - | -240 min |
| C2P-Visitor-1.6 | Charge all HT batteries | - | -240 min |
| C2P-Visitor-1.7 | Test all 5 Offense helmet modules on FS2 (Simplex and Duplex) | - | -240 min |
| C2P-Visitor-1.8 | Test all 5 Defense helmet modules on FS2 (Simplex and Duplex) | - | -240 min |
| C2P-Visitor-1.9 | Test both Local cutoff switches on FS2 | - | -240 min |
| C2P-Visitor-1.1 | Switch power and RF to "FS1" position | - | -240 min |
| C2P-Visitor-1.11 | Test all 5 Offense helmet modules on FS1 (Simplex and Duplex) | - | -240 min |
| C2P-Visitor-1.12 | Test all 5 Defense helmet modules on FS1 (Simplex and Duplex) | - | -240 min |
| C2P-Visitor-1.13 | 10 helmet modules are ready for pickup by equipment manager at 3.5 hours | - | -240 min |
| C2P-Visitor-1.14 | Confirm both power cables are connected to line power | - | -240 min |
| C2P-Visitor-1.15 | Test one Local Cutoff switch on FS1 repeater. | - | -240 min |
| C2P-Visitor-1.16 | Test offense power level to far right endline | - | -240 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-2.1 | Login to EFC.NFL.NET | EFC (1.1-1.11) | -240 min |
| EFC-2.2 | Check for any late frequency requests to coordinate | - | -240 min |
| EFC-2.3 | Greet key game personnel. Connect with any customer who raised a concern or didn't properly submit their request through EFC, or may need further assistance | - | -240 min |
| EFC-2.4 | EFC checks in with Home/Visiting Radio and media on press box level | - | -240 min |
| EFC-2.5 | Check in with NFL Enhanced Audio | - | -240 min |

## FTR

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| FTR-1.1 | Post 'FTR on-site' in the Football Technology WhatsApp group | WiFi Results (4 Hours Prior) & C2P Home (1.1-1.17) & C2P Visitor (1.1-1.17) | -240 min |
| FTR-1.2 | Pick up field access armband | - | -240 min |
| FTR-1.3 | Technology cart is placed on field in proper location and orientation | - | -240 min |
| FTR-1.4 | Primary and secondary OpticalCon cables are properly connected. | - | -240 min |
| FTR-1.5 | Ensure proper antenna placement | - | -240 min |
| FTR-1.6 | Post photo of Home Sideline Tech cart with antennas to the WhatsApp group | - | -240 min |
| FTR-1.7 | Power Check (regular season home games 1, 5 and 10) | - | -240 min |
| FTR-1.8 | Primary and secondary switches have green link lights on optical SFPs | - | -240 min |
| FTR-1.9 | Cables for C2P interfaces and bridges are neat and tidy | - | -240 min |
| FTR-1.1 | Surface tablet is on and logged in | - | -240 min |
| FTR-1.11 | Green Go batteries on charge | - | -240 min |
| FTR-1.12 | Tiny PC is on and logged in | - | -240 min |
| FTR-1.13 | Phone in tech cart is operational (gets dial-tone) | - | -240 min |
| FTR-1.14 | Phone strobe and loudspeaker (alerter) are functional. | - | -240 min |
| FTR-1.15 | RCO is plugged in and operational | - | -240 min |
| FTR-1.16 | Surface charging cart is plugged into port #39 of IO panel | - | -240 min |
| FTR-1.17 | Confirm spare OpticalCon cable is located in bottom drawer of cart | - | -240 min |
| FTR-1.18 | Confirm 15 - 100 Ethercon cables are available on the sideline | - | -240 min |
| FTR-1.19 | Confirm IVR monitor is receiving video on the primary and secondary AJA units | - | -240 min |
| FTR-1.2 | Confirm there are 3 dual-muff headsets for IVR use (2 in monitor door and 1 in phone door) | - | -240 min |
| FTR-1.21 | Confirm both IVR belt packs are operational | - | -240 min |
| FTR-1.22 | Cart is weather tight | - | -240 min |
| FTR-1.23 | Confirm Cutoff Pack #3 is stored in home technology cart | - | -240 min |
| FTR-2.1 | Technology cart is placed on field in proper location and orientation | WiFi Results (4 Hours Prior) & C2P Home (1.1-1.17) & C2P Visitor (1.1-1.17) | -240 min |
| FTR-2.2 | Fiber toolkit inventory | - | -240 min |
| FTR-2.3 | Primary and secondary OpticalCon cables are properly connected | - | -240 min |
| FTR-2.4 | Ensure proper antenna placement | - | -240 min |
| FTR-2.5 | Post photo of Visitor Sideline Tech cart with antennas to the WhatsApp group | - | -240 min |
| FTR-2.6 | Power Check (home games 1, 5 and 10) | - | -240 min |
| FTR-2.7 | Primary and secondary switches have green link lights on optical SFPs | - | -240 min |
| FTR-2.8 | Cables for C2P interfaces and bridges are neat and tidy | - | -240 min |
| FTR-2.9 | Surface tablet is on and logged in | - | -240 min |
| FTR-2.1 | Green Go batteries on charge | - | -240 min |
| FTR-2.11 | Tiny PC is on and logged in | - | -240 min |
| FTR-2.12 | Phone in tech cart is operational - gets dial-tone | - | -240 min |
| FTR-2.13 | Phone strobe and loudspeaker (alerter) are functional. | - | -240 min |
| FTR-2.14 | RCO is plugged in and operational | - | -240 min |
| FTR-2.15 | Surface charging cart is plugged into port #39 of IO panel | - | -240 min |
| FTR-2.16 | Confirm spare OpticalCon cable is located in bottom drawer of cart | - | -240 min |
| FTR-2.17 | Confirm 15 - 100 Ethercon cables are available on the sideline | - | -240 min |
| FTR-2.18 | Confirm IVR monitor is receiving video on the primary and secondary AJA units | - | -240 min |
| FTR-2.19 | Confirm there are 3 dual-muff headsets for IVR use (2 in monitor door and 1 in phone door) | - | -240 min |
| FTR-2.2 | Confirm both IVR belt packs are operational | - | -240 min |
| FTR-2.21 | Cart is weather tight | - | -240 min |
| FTR-2.22 | Work with IR Tech and IRFO to ensure the Riedel O2O Antenna B is mounted using the Magic Arm and connected via ethernet cable on the opposite sideline railing diagonal from the Instant Replay Field Un | - | -240 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-6 | Field Checks (if time permitting) | Hawk-Eye (5.1-5.3) | -240 min |
| Hawk-Eye-6.1 | Primary AND secondary UTH reaching field cart? | - | -240 min |
| Hawk-Eye-6.2 | Home IVR screen reaching home sideline tech cart on primary AND secondary? | - | -240 min |
| Hawk-Eye-6.3 | Visitor IVR screen reaching visitor sideline tech cart on primary AND secondary? | - | -240 min |
| Hawk-Eye-6.4 | Continue to monitor for any remaining missing feeds | - | -240 min |

## IR Tech

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IR Tech-1.1 | Clock into UKG upon arrival to the stadium and post 'IR Tech on-site' in the Football Technology WhatsApp group | EFC (2.1-2.5) | -240 min |
| IR Tech-1.2 | Confirm IR Field Operators are onsite and setting up field equipment | - | -240 min |
| IR Tech-1.3 | Work with Hawk-Eye tech to ensure booth is fully setup and operational. Ensure all IR booth rack connections of fiber, video to coaches booths, C2P cutoffs, Riedel High antenna are all working. Setup | - | -240 min |
| IR Tech-1.5 | Test Riedel audio communication within booth on the Replay channel | - | -240 min |
| IR Tech-1.6 | Reboot C2P cutoff switches. | - | -240 min |
| IR Tech-1.7 | Confirm with field techs that O2O and field tablets are being charged and protected from inclement weather | - | -240 min |
| IR Tech-1.8 | Test All29 camera and control. Ensure camera is framed to include all of the field, from goal post to goal post | - | -240 min |
| IR Tech-1.1 | Test Riedel audio communication between booth and field unit and tablets | - | -240 min |
| IR Tech-1.11 | Confirm UTH confidence monitor is seeing video from AMGC | - | -240 min |
| IR Tech-1.12 | Check shared folder for Hawk-Eye Monitor placement preference by visiting team. Link is to the right in the Steps column. | - | -240 min |

## IVRS

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IVRS-1.0 | Booth | EFC (2.1-2.5) | -240 min |
| IVRS-1.1 | Clock into UKG upon arrival to the stadium and post 'IVRS on-site' in the Football Technology WhatsApp group | - | -240 min |
| IVRS-1.2 | Setup equipment for Tech, AT Spotter and UNC positions | - | -240 min |
| IVRS-1.3 | Test GreenGo Audio Communication within the booth | - | -240 min |
| IVRS-1.4 | Confirm Program Audio is being received on ATC Spotter headsets | - | -240 min |
| IVRS-1.5 | Test GreenGo Audio Communication with the field | - | -240 min |
| IVRS-1.6 | Ensure all medical radios are fully charged | - | -240 min |
| IVRS-1.7 | Turn on radios and do a quick communications test | - | -240 min |
| IVRS-2.0 | Field - Home | EFC (2.1-2.5) | -240 min |
| IVRS-2.1 | Turn on radios and do a quick communications test | - | -240 min |
| IVRS-2.2 | Power up and charge UNC tablets on Sideline Cart | - | -240 min |
| IVRS-2.3 | Confirm primary and secondary AJAs have lock lights on both sideline carts | - | -240 min |
| IVRS-2.4 | Test video feed from primary and secondary AJA on sideline cart | - | -240 min |
| IVRS-2.5 | Confirm Program Audio is being received on IVRS Tech headsets | - | -240 min |
| IVRS-2.6 | Deliver medical radios to Home team locker room attendant at the 3hr mark (if applicable) | - | -240 min |
| IVRS-3.0 | Field - Visitor | EFC (2.1-2.5) | -240 min |
| IVRS-3.1 | Turn on radios and do a quick communications test | - | -240 min |
| IVRS-3.2 | Power up and charge UNC tablets on Sideline Cart | - | -240 min |
| IVRS-3.3 | Confirm primary and secondary AJAs have lock lights on both sideline carts | - | -240 min |
| IVRS-3.4 | Test video feed from primary and secondary AJA on sideline cart | - | -240 min |
| IVRS-3.5 | Confirm Program Audio is being received on IVRS Tech headsets | - | -240 min |
| IVRS-3.6 | Deliver medical radios to Visiting team locker room attendant at the 3hr mark. Inform visiting team that you will pick up the radios from them after the game. | - | -240 min |

## O2O

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| O2O-1.1 | Ensure all 15 packs are charging and fully charged (solid green) | EFC (2.1-2.5) | -240 min |
| O2O-1.2 | Antenna 1 is mounted on IRFU and has green status LED | - | -240 min |
| O2O-1.3 | Work with FTR and IRFO to ensure the Riedel O2O Antenna B is mounted using the Magic Arm and connected via ethernet cable on the opposite sideline railing diagonal from the Instant Replay Field Unit. | - | -240 min |
| O2O-1.4 | Test one belt pack | - | -240 min |
| O2O-1.5 | Test all seven "#2" belt packs | - | -240 min |
| O2O-1.6 | Test all seven "#1" belt packs | - | -240 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-1.1 | Clock into UKG upon arrival to the stadium. In WhatsApp, post 'Purple Hats on-site' and include where each PH will be stationed for the game. | EFC (2.1-2.5) | -240 min |
| SVS-Home-1.2 | Give a heads up to the StillShot Operator to warn them about profile updates in game. In addition, please ensure they're filling out the team properties correctly before going into the game. | - | -240 min |
| SVS-Home-1.3 | Setup of DVSport Booth StillShot Case | - | -240 min |
| SVS-Home-1.4 | Connect the DVSport Booth StillShot Case to the NFL Network Switch | - | -240 min |
| SVS-Home-1.5 | Connect the Coaches Location to the NFL Network Switch in Port 28-40 | - | -240 min |
| SVS-Home-1.6 | Setup Coach Surfaces | - | -240 min |
| SVS-Home-1.7 | Locate Surface Pens and Check Batteries | - | -240 min |
| SVS-Home-1.8 | Distribute Radios and Headsets | - | -240 min |
| SVS-Home-2.1 | Charging cart is powered and all Surface devices are charging | EFC (2.1-2.5) | -240 min |
| SVS-Home-2.2 | Test All Surface Pens | - | -240 min |
| SVS-Home-2.3 | Ensure team names are correct | - | -240 min |
| SVS-Home-2.4 | Connect the charging cart to the NFL Technology Cart in SVSUP1 (Port 39). | - | -240 min |
| SVS-Home-2.5 | Connect the charging cart to the NFL Technology Cart in SVSUP1 (Port 39). | - | -240 min |
| SVS-Home-2.6 | Charging Cart Best Practice Setup Checks | - | -240 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-1.1 | Clock into UKG upon arrival to the stadium. In WhatsApp, post 'Purple Hats on-site' and include where each PH will be stationed for the game. | EFC (2.1-2.5) | -240 min |
| SVS-Visitor-1.2 | Give a heads up to the StillShot Operator to warn them about profile updates in game. In addition, please ensure they're filling out the team properties correctly before going into the game. | - | -240 min |
| SVS-Visitor-1.3 | Setup of DVSport Booth StillShot Case | - | -240 min |
| SVS-Visitor-1.4 | Connect the DVSport Booth StillShot Case to the NFL Network Switch | - | -240 min |
| SVS-Visitor-1.5 | Connect the Coaches Location to the NFL Network Switch in Port 28-40 | - | -240 min |
| SVS-Visitor-1.6 | Setup Coach Surfaces | - | -240 min |
| SVS-Visitor-1.7 | Locate Surface Pens and Check Batteries | - | -240 min |
| SVS-Visitor-1.8 | Distribute Radios and Headsets | - | -240 min |
| SVS-Visitor-2.1 | Charging cart is powered and all Surface devices are charging | EFC (2.1-2.5) | -240 min |
| SVS-Visitor-2.2 | Test All Surface Pens | - | -240 min |
| SVS-Visitor-2.3 | Ensure team names are correct | - | -240 min |
| SVS-Visitor-2.4 | Connect the charging cart to the NFL Technology Cart in SVSUP1 (Port 39). | - | -240 min |
| SVS-Visitor-2.5 | Charging Cart Best Practice Setup Checks | - | -240 min |

## WiFi

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| WiFi-1.1 | Post 'WiFi or Network Tech on site' in the Football Technology WhatsApp group | EFC (2.1-2.5) | -240 min |
| WiFi-1.2 | Pick up field access armband | - | -240 min |
| WiFi-1.3 | Mount antennas on Visitor Sideline cart | - | -240 min |
| WiFi-1.4 | Conduct Visitor WiFi test using Insider tool to ensure channels in use are clean. | - | -240 min |
| WiFi-1.5 | Perform Visitor Left-to-Right Roaming test | - | -240 min |
| WiFi-1.6 | Perform Visitor Right-to-Left Roaming test | - | -240 min |
| WiFi-1.7 | Record Signal Strength and Data Speeds on Visitor Sideline every 5 yds at the 6ft white border | - | -240 min |
| WiFi-1.8 | Record Signal Strength and Data Speeds on Visitor Sideline every 5 yds at the bench | - | -240 min |
| WiFi-1.09 | Mount antennas on Home Sideline cart | - | -240 min |
| WiFi-1.1 | Conduct Home WiFi test using Insider tool to ensure channels in use are clean. | - | -240 min |
| WiFi-1.11 | Perform Home Left-to-Right Roaming test | - | -240 min |
| WiFi-1.12 | Perform Home Right-to-Left Roaming test | - | -240 min |
| WiFi-1.13 | Record Signal Strength and Data Speeds on Home Sideline every 5 yds at the 6ft white border | - | -240 min |
| WiFi-1.14 | Record Signal Strength and Data Speeds on Home Sideline every 5 yds at the bench | - | -240 min |
| WiFi-1.15 | Record the Antennae Setup angles | - | -240 min |

# Milestone 3: Inspections

Timing: T-4 to T-3 Hours | Inspections & Pre-Game Technology Check

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-2.2 | Install 2 simplex antennas on Sideline Tech Cart | - | -210 min |
| C2P-Home-2.3 | Connect RCO to technology cart | - | -210 min |
| C2P-Home-2.4 | Base Station Tests Test simplex FS1 play call on Offense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.5 | Test simplex FS2 play call on Offense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.6 | Test simplex FS1 play call on Defense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.7 | Test simplex FS2 play call on Defense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.8 | Test simplex FS1 Offense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.9 | Test simplex FS2 Offense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.1 | Test simplex FS1 Defense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.11 | Test simplex FS2 Defense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Home-2.12 | Confirm that RCO#1 engages the cutoff operation of the repeater when the cutoff switch is engaged and disengaged. | - | -210 min |
| C2P-Home-2.13 | Confirm that RCO#2 engages the cutoff operation of the repeater when the cutoff switch is engaged and disengaged. | - | -210 min |
| C2P-Home-2.14 | Return Cutoff #3 to Storage | - | -210 min |
| C2P-Home-2.15 | Disconnect RCO#2 from "Cutoff" port of the C2P IO Panel | - | -210 min |
| C2P-Home-2.16 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -210 min |
| C2P-Home-2.17 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -210 min |
| C2P-Home-2.18 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -210 min |
| C2P-Home-2.19 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -210 min |
| C2P-Home-2.2 | Confirm time of fully test with Yellow Hat and Equipment Manager | - | -210 min |
| C2P-Home-2.21000000000001 | Confirm home team C2C tech and equipment manager have successfully tested the helmet modules | - | -210 min |
| C2P-Home-2.22000000000001 | Document radio pick up by team contacts (names of team contact(s), role at club, and time of day in pregame). Also record total number of radios distributed to Club contact. | - | -210 min |
| C2P-Home-3.1 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -120 min |
| C2P-Home-3.2 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -120 min |
| C2P-Home-3.3 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -120 min |
| C2P-Home-3.4 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -120 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-2.2 | Install 2 simplex antennas on Sideline Tech Cart | - | -210 min |
| C2P-Visitor-2.3 | Connect RCO to technology cart | - | -210 min |
| C2P-Visitor-2.4 | Base Station Tests Test simplex FS1 play call on Offense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.5 | Test simplex FS2 play call on Offense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.6 | Test simplex FS1 play call on Defense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.7 | Test simplex FS2 play call on Defense Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.8 | Test simplex FS1 Offense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.9 | Test simplex FS2 Offense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.1 | Test simplex FS1 Defense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.11 | Test simplex FS2 Defense play call on Spare Base Station using handheld mic to Blue Radio | - | -210 min |
| C2P-Visitor-2.12 | Confirm that RCO#1 engages the cutoff operation of the repeater when the cutoff switch is engaged and disengaged. | - | -210 min |
| C2P-Visitor-2.13 | Confirm that RCO#2 engages the cutoff operation of the repeater when the cutoff switch is engaged and disengaged. | - | -210 min |
| C2P-Visitor-2.14 | Return Cutoff #3 to Storage | - | -210 min |
| C2P-Visitor-2.15 | Disconnect RCO#2 from "Cutoff" port of the C2P IO Panel | - | -210 min |
| C2P-Visitor-2.16 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -210 min |
| C2P-Visitor-2.17 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -210 min |
| C2P-Visitor-2.18 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -210 min |
| C2P-Visitor-2.19 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -210 min |
| C2P-Visitor-2.2 | Confirm time of fully test with Yellow Hat and Equipment Manager | - | -210 min |
| C2P-Visitor-2.21000000000001 | Confirm home team C2C tech and equipment manager have successfully tested the helmet modules | - | -210 min |
| C2P-Visitor-2.22000000000001 | Document radio pick up by team contacts (names of team contact(s), role at club, and time of day in pregame). Also record total number of radios distributed to Club contact. | - | -210 min |
| C2P-Visitor-3.1 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -120 min |
| C2P-Visitor-3.2 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -120 min |
| C2P-Visitor-3.3 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -120 min |
| C2P-Visitor-3.4 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -120 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-3.1 | Check in at media field level room, and then check in with Home/Visiting sidelines, Yellow Hats (C2C techs) & Orange Hats (C2P techs) | FTR (3.1) | -180 min |
| EFC-4.1 | Double check with house audio for Ref mic test | IR Tech (3.1-3.3) | -120 min |
| EFC-4.2 | Check in with Zebra | - | -120 min |

## FTR

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| FTR-3.1 | Review and close any open items if you have received RMA'd equipment | IR Tech (2.2-2.7) | -180 min |
| FTR-4.1 | Check in with visitor sideline Purple Hat to confirm they're operational and game ready | WiFi (3.1) | -120 min |
| FTR-4.2 | Check in with home sideline Purple Hat to confirm they're operational and game ready | - | -120 min |
| FTR-4.3 | Meet the Football Operations representative, if there's one present, and make sure you have his/her contact information from the Travel Sheet. | - | -120 min |
| FTR-4.4 | Test Green Hat communication | - | -120 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-6.5 | If no other outstanding issues, be on hand at instant replay booth for 3 hour check | - | -180 min |
| Hawk-Eye-6.6 | If no other outstanding issues, be on hand at instant replay booth for 2 hour check | - | -120 min |

## IR Tech

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IR Tech-2.1 | System Check between Booth, Field and AMGC, including O2O | O2O (2.1) & WiFi (2.1-2.3) & SVS Visitor (3.1-3.7, 4.1-4.10) & SVS Home (3.1-3.7, 4.1-4.10) | -180 min |
| IR Tech-2.2 | Replay Official equipment has been checked by Official | - | -180 min |
| IR Tech-2.3 | Home coaches' booth is receiving Truck feed on Haivision Decoders (regular season home games 1, 5 and game 10) | - | -180 min |
| IR Tech-2.4 | Home coaches' booth is receiving Truck Feed on Decimators | - | -180 min |
| IR Tech-2.5 | Visitor coaches' booth is receiving truck feed on Haivision Decoders (regular season home games 1, 5 and game 10) | - | -180 min |
| IR Tech-2.6 | Visitor coaches' booth is receiving Truck Feed on Decimators | - | -180 min |
| IR Tech-2.7 | Post in your Club WhatsApp thread confirming all coaches' booth monitors are receiving the Truck Feed | - | -180 min |
| IR Tech-3.1 | System Check between Booth, Field and AMGC (and possible additional O2O check) | O2O (3.1) | -120 min |
| IR Tech-3.2 | Replay Official Meeting in IR Booth regarding operating procedures | - | -120 min |
| IR Tech-3.3 | Verify with Hawk-Eye tech that Back Judge Smartwatch has latest software update and is charged in full. Ensure watches are given to IRFO to hand one watch off to Back Judge for the game and then swapp | - | -120 min |

## O2O

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| O2O-2.1 | Field walk test | O2O (1.1-1.6) | -180 min |
| O2O-3.1 | Confirm Ref Mic is heard on Riedel Panel (NFL branded CoachComm headset) at IR Field Unit during ref mic test. Program Audio and Ref Mic buttons need to both be latched on by pressing the button on t | O2O (2.1) | -120 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-3.1 | Test Booth StillShot System (power on all servers and Surfaces. Start 'New Game' in DVSport software) | SVS Home (2.1-2.6) | -180 min |
| SVS-Home-3.2 | Verify feeds, network to Surfaces, and plays to field | - | -180 min |
| SVS-Home-3.3 | Validating Sideline and Endzone Feeds from Home Coaches booth Encoder back to NFL Office. | - | -180 min |
| SVS-Home-3.4 | Sync up with DVSport representative in prep for giving all clear at 90 mins | - | -180 min |
| SVS-Home-3.5 | Test the Failover Scenario of Primary StillShot Server: | - | -180 min |
| SVS-Home-3.6 | Check Repeater Status | - | -180 min |
| SVS-Home-3.7 | Run DVSport Network Test and verify every item passes. | - | -180 min |
| SVS-Home-4.1 | All SVS Tech working as expected | SVS Home (3.1-3.7) | -180 min |
| SVS-Home-4.2 | Ensure locking gate is securely closed to protect the server power buttons | - | -180 min |
| SVS-Home-4.3 | Confirm SS Monitors and all peripherals are operational | - | -180 min |
| SVS-Home-4.4 | SL and EZ feeds for Pri and Sec | - | -180 min |
| SVS-Home-4.5 | All Surfaces tested and receiving plays | - | -180 min |
| SVS-Home-4.6 | Test at least one tablet via hardwire connection | - | -180 min |
| SVS-Home-4.6 | Test Failover of all Booth Surfaces | - | -180 min |
| SVS-Home-4.7 | Test Failover of all Sideline Surfaces | - | -180 min |
| SVS-Home-4.8 | WiFi working as expected | - | -180 min |
| SVS-Home-4.9 | Report any other issues | - | -180 min |
| SVS-Home-4.1 | Verify that correct Teams and team colors are showing on GSIS Stats Tile on Surfaces. | - | -180 min |
| SVS-Home-5.1 | Receive Pre-Game report from DVSport | SVS Home (4.1-4.10) | -120 min |
| SVS-Home-5.2 | Verify location of Analytics Laptop in the booth | - | -120 min |
| SVS-Home-5.3 | Set up Analytics Laptop | - | -120 min |
| SVS-Home-5.4 | First Home Game only Set Up | - | -120 min |
| SVS-Home-5.5 | Turn on laptop, it should auto login to 'Analyst' User and Excel should launch | - | -120 min |
| SVS-Home-5.6 | Ensure that no user is still logged into Excel from the last game | - | -120 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-3.1 | Test Booth StillShot System (power on all servers and Surfaces. Start 'New Game' in DVSport software) | SVS Visitor (2.1-2.5) | -180 min |
| SVS-Visitor-3.2 | Verify feeds, network to Surfaces, and plays to field | - | -180 min |
| SVS-Visitor-3.3 | Validating Sideline and Endzone Feeds from Home Coaches booth Encoder back to NFL Office. | - | -180 min |
| SVS-Visitor-3.4 | Sync up with DVSport representative in prep for giving all clear at 90 mins | - | -180 min |
| SVS-Visitor-3.5 | Test the Failover Scenario of Primary StillShot Server: | - | -180 min |
| SVS-Visitor-3.6 | Check Repeater Status | - | -180 min |
| SVS-Visitor-3.7 | Run DVSport Network Test and verify every item passes. | - | -180 min |
| SVS-Visitor-4.1 | All SVS Tech working as expected | SVS Visitor (3.1-3.7) | -180 min |
| SVS-Visitor-4.2 | Ensure locking gate is securely closed to protect the server power buttons | - | -180 min |
| SVS-Visitor-4.3 | Confirm SS Monitors and all peripherals are operational | - | -180 min |
| SVS-Visitor-4.4 | SL and EZ feeds for Pri and Sec | - | -180 min |
| SVS-Visitor-4.5 | All Surfaces tested and receiving plays | - | -180 min |
| SVS-Visitor-4.6 | Test at least one tablet via hardwire connection | - | -180 min |
| SVS-Visitor-4.6 | Test Failover of all Booth Surfaces | - | -180 min |
| SVS-Visitor-4.7 | Test Failover of all Sideline Surfaces | - | -180 min |
| SVS-Visitor-4.8 | WiFi working as expected | - | -180 min |
| SVS-Visitor-4.9 | Report any other issues | - | -180 min |
| SVS-Visitor-4.1 | Verify that correct Teams and team colors are showing on GSIS Stats Tile on Surfaces. | - | -180 min |
| SVS-Visitor-5.1 | Receive Pre-Game report from DVSport | SVS Visitor (4.1-4.10) | -120 min |
| SVS-Visitor-5.2 | Verify location of Analytics Laptop in the booth | - | -120 min |
| SVS-Visitor-5.3 | Set up Analytics Laptop | - | -120 min |
| SVS-Visitor-5.4 | First Home Game only Set Up | - | -120 min |
| SVS-Visitor-5.5 | Turn on laptop, it should auto login to 'Analyst' User and Excel should launch | - | -120 min |
| SVS-Visitor-5.6 | Ensure that no user is still logged into Excel from the last game | - | -120 min |

## WiFi

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| WiFi-2.1 | Conduct Home WiFi test using Insider tool to ensure channels in use are clean. | WiFi (1.1-1.15) | -180 min |
| WiFi-2.2 | Conduct Visitor WiFi test using Insider tool to ensure channels in use are clean. | - | -180 min |
| WiFi-2.3 | Retrieve Purple Hat radio | - | -180 min |
| WiFi-3.1 | Check In with Purple Hats and Validate Game Readiness | WiFi (2.1-2.3) | -120 min |

# Milestone 4: Broadcast Ready

Timing: T-3 to Kickoff | Broadcast & Technician Readiness

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-4.1 | Tech is in-place on field and must remain on field from now until to end of game | - | -60 min |
| C2P-Home-4.2 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -60 min |
| C2P-Home-4.3 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -60 min |
| C2P-Home-4.4 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -60 min |
| C2P-Home-4.5 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -60 min |
| C2P-Home-4.6 | Disconnect RCO from repeater | - | -60 min |
| C2P-Home-5.0 | Throughout the Game | - | -60 min |
| C2P-Home-5.2 | Confirm you're not seeing RFI on the base station LED indicators | - | -60 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-4.1 | Tech is in-place on field and must remain on field from now until to end of game | - | -60 min |
| C2P-Visitor-4.2 | Listen to CSQ FS-1 Hi for 5 minutes. | - | -60 min |
| C2P-Visitor-4.3 | Listen to CSQ FS-1 Lo for 5 minutes. | - | -60 min |
| C2P-Visitor-4.4 | Listen to CSQ FS-2 Hi for 5 minutes. | - | -60 min |
| C2P-Visitor-4.5 | Listen to CSQ FS-2 Lo for 5 minutes. | - | -60 min |
| C2P-Visitor-4.6 | Disconnect RCO from repeater | - | -60 min |
| C2P-Visitor-5.0 | Throughout the Game | - | -60 min |
| C2P-Visitor-5.2 | Confirm you're not seeing RFI on the base station LED indicators | - | -60 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-5.1 | One EFC reports to the visitor sideline and remains there the entire game | IR Tech (4.1-4.4) | -60 min |
| EFC-6.1 | From either the home or visitor 50 yard line, at least 6 feet behind the bench area, scan CBRS Band (3500 to 3700 MHz) on max hold and post a picture, along with the location the scan was taken (ex: V | IR Tech (5.1) | -30 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-6.7 | If no other outstanding issues, be on hand at instant replay booth for 50 min check | - | -50 min |

## IR Tech

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IR Tech-4.1 | Field Stations are ready for Referee equipment check | IVRS (5.1-5.3) | -60 min |
| IR Tech-4.2 | Final System check between Booth, Field and AMGC | - | -60 min |
| IR Tech-4.3 | Home Coaches Booth is receiving Truck Feed on both monitors | - | -60 min |
| IR Tech-4.4 | Visitor Coaches Booth is receiving Truck Feed on both monitors | - | -60 min |
| IR Tech-5.1 | Referee has completed field station readiness | O2O (4.1) | -50 min |
| IR Tech-6.0 | End Of Game | - | -50 min |
| IR Tech-6.2 | Turn off all monitors on front row. | - | -50 min |
| IR Tech-6.3 | Ensure Hawk-Eye has turned of their viewing stations in IR Booth | - | -50 min |
| IR Tech-6.4 | Turn off UPS in IR rack | - | -50 min |
| IR Tech-6.5 | Return game day radio | - | -50 min |
| IR Tech-6.6 | Moisture control | - | -50 min |
| IR Tech-6.5 | Complete your postgame report at GMS.NFL.NET within 24 hours of game end | - | -50 min |
| IR Tech-6.7 | Clock out of UKG when you leave the stadium | - | -50 min |

## IVRS

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IVRS-4.1 | Field IVR Operators attend 60-Minute Meeting | IVRS (3.1-3.6) | -60 min |
| IVRS-4.2 | Field Operators issue Independent Medical Radios to UNCs, AMP, and ERP | - | -60 min |
| IVRS-5.1 | Distribute Independent radios to booth UNC and AT Spotters | IVRS (4.1-4.2) | -50 min |
| IVRS-5.2 | AT Spotter initiates medical time out test on ATC belt pack and radio with referee | - | -50 min |
| IVRS-5.3 | Confirm system is operational for kickoff | - | -50 min |

## O2O

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| O2O-4.1 | Confirm officials can communicate with each other as well as to the IR booth | O2O (3.1) | -50 min |
| O2O-5.0 | End Of Game | - | -50 min |
| O2O-5.2 | Confirm 4 spare headsets are stored in case | - | -50 min |
| O2O-5.3 | Confirm 2 spare PTT buttons are stored in case | - | -50 min |
| O2O-5.4 | Moisture control, when necessary | - | -50 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-6.2 | NEW - Confirm profiles are loaded | - | -90 min |
| SVS-Home-6.3 | Report 'All Clear' to DVSport | - | -90 min |
| SVS-Home-6.4 | Greet Team Analyst and Oversee Analyst login to Excel | - | -90 min |
| SVS-Home-6.5 | Observe or assist Analyst to launch the Gameday file | - | -90 min |
| SVS-Home-7.1 | Confirm with StillShot Operator they're starting the actual game. They must alert you if they start another game before kick. If they prefer the Purple Hat to start the game, please do so. There shoul | SVS Home (6.1-6.5) | -30 min |
| SVS-Home-7.2 | Once Purple Hat gets final new game confirmation, Purple Hat must check both primary and secondary on a tablet to ensure the team on the top bar is correct, and on the About tab (also in the hub view | - | -30 min |
| SVS-Home-7.3 | Sideline Purple Hats track # of devices | - | -30 min |
| SVS-Home-7.4 | All Purple Hats are in position for game | - | -30 min |
| SVS-Home-7.5 | Exactly at 30 mins, Relaunch script and verify that Analaytics Tablets are unlocked | - | -30 min |
| SVS-Home-7.6 | Check in with Analyst that the spreadsheet properly unlocked and that they are good | - | -30 min |
| SVS-Home-8.1 | Ensure video signals for Hi50 and HiEZ are crisp and there's no flickering | SVS Home (7.1-7.6) | -30 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-6.2 | NEW - Confirm profiles are loaded | - | -90 min |
| SVS-Visitor-6.3 | Report 'All Clear' to DVSport | - | -90 min |
| SVS-Visitor-6.4 | Greet Team Analyst and Oversee Analyst login to Excel | - | -90 min |
| SVS-Visitor-6.5 | Observe or assist Analyst to launch the Gameday file | - | -90 min |
| SVS-Visitor-7.1 | Confirm with StillShot Operator they're starting the actual game. They must alert you if they start another game before kick. If they prefer the Purple Hat to start the game, please do so. There shoul | SVS Visitor (6.1-6.5) | -30 min |
| SVS-Visitor-7.2 | Once Purple Hat gets final new game confirmation, Purple Hat must check both primary and secondary on a tablet to ensure the team on the top bar is correct, and on the About tab (also in the hub view | - | -30 min |
| SVS-Visitor-7.3 | Sideline Purple Hats track # of devices | - | -30 min |
| SVS-Visitor-7.4 | All Purple Hats are in position for game | - | -30 min |
| SVS-Visitor-7.5 | Exactly at 30 mins, Relaunch script and verify that Analaytics Tablets are unlocked | - | -30 min |
| SVS-Visitor-7.6 | Check in with Analyst that the spreadsheet properly unlocked and that they are good | - | -30 min |
| SVS-Visitor-8.1 | Ensure video signals for Hi50 and HiEZ are crisp and there's no flickering | - | -30 min |

## WiFi

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| WiFi-4.2 | Conduct Visitor WiFi test using Insider tool to ensure channels in use are clean. | - | -90 min |
| WiFi-4.3 | Post Status of WiFi on CLUB CHAT | - | -90 min |
| WiFi-5.1 | Check In with Purple Hats and confirm Game Ready Status. ROTATE SIDES EACH QUARTER. Continue to Check In with the FTR and Purple Hats for any issues. | WiFi (4.1-4.3) | -30 min |
| WiFi-5.2 | Post Status of WiFi on CLUB CHAT | - | -30 min |
| WiFi-6.1 | Run final pregame speed tests. Start on the Home Sideline and rotate every quarter. Check-in periodically with the Gray & Purple Hats for any issues. | WiFi (5.1-5.2) | -30 min |

# Milestone 5: Live Monitoring

Timing: During Game | Live Monitoring & Real-Time Adjustments

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-5.1 | Monitor the Hi frequency of the other FS (1 or 2). | - | 0 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-5.1 | Monitor the Hi frequency of the other FS (1 or 2). | - | 0 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-7.1 | Assist users who may report interference problems | Game Started | 0 min |
| EFC-8.0 | End Of Game | - | 0 min |
| EFC-8.2 | Pack up equipment, clock out of UKG and head home. | - | 0 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-6.8 | Be on standby throughout game near instant replay and IVR booths to troubleshoot as needed | - | 0 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-9.1 | After 1st Play, Check Secondary from Surface | Game Started | 0 min |
| SVS-Home-9.2 | Monitor devices throughout game (lookout for direct sunlight/rain etc) | - | 0 min |
| SVS-Home-9.3 | Monitor battery throughout game | - | 0 min |
| SVS-Home-9.4 | Monitor issues with Analytics Tablet throughout the game | - | 0 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-9.1 | After 1st Play, Check Secondary from Surface | Game Started | 0 min |
| SVS-Visitor-9.2 | Monitor devices throughout game (lookout for direct sunlight/rain etc) | - | 0 min |
| SVS-Visitor-9.3 | Monitor battery throughout game | - | 0 min |
| SVS-Visitor-9.4 | Monitor issues with Analytics Tablet throughout the game | - | 0 min |

# Milestone 6: Post-Game

Timing: End of Game | Post-Game Equity Review & Departure

## C2P-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Home-6.1 | Collect and store all 4 red radios | Game Ended | 0 min |
| C2P-Home-6.2 | Collect and store all 10 helmet modules | - | 0 min |
| C2P-Home-6.3 | Collect and store all 5 blue monitor radios and earpieces | - | 0 min |
| C2P-Home-6.4 | Store 1 orange tech radio | - | 0 min |
| C2P-Home-6.5 | Remove 50 ft Ethercon cable from RCO and Tech Cart and store in the phone cart | - | 0 min |
| C2P-Home-6.6 | Remove and store all antennas (2 short on Tech Cart, 1 on SCC Cart) | - | 0 min |
| C2P-Home-6.7 | Power off UPS | - | 0 min |
| C2P-Home-6.8 | Disconnect Power | - | 0 min |
| C2P-Home-6.9 | Moisture control | - | 0 min |
| C2P-Home-6.1 | Complete your game report on GMS.NFL.Net within 4 hours of game end | - | 0 min |

## C2P-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| C2P-Visitor-6.1 | Collect and store all 4 red radios | Game Ended | 0 min |
| C2P-Visitor-6.2 | Collect and store all 10 helmet modules | - | 0 min |
| C2P-Visitor-6.3 | Collect and store all 5 blue monitor radios and earpieces | - | 0 min |
| C2P-Visitor-6.4 | Store 1 orange tech radio | - | 0 min |
| C2P-Visitor-6.5 | Remove 50 ft Ethercon cable from RCO and Tech Cart and store in the phone cart | - | 0 min |
| C2P-Visitor-6.6 | Remove and store all antennas (2 short on Tech Cart, 1 on SCC Cart) | - | 0 min |
| C2P-Visitor-6.7 | Power off UPS | - | 0 min |
| C2P-Visitor-6.8 | Disconnect Power | - | 0 min |
| C2P-Visitor-6.9 | Moisture control | - | 0 min |
| C2P-Visitor-6.1 | Complete your game report on GMS.NFL.Net within 4 hours of game end | - | 0 min |

## EFC

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| EFC-8.1 | Complete GMS postgame report at https://GMS.NFL.NET | Game Ended | 0 min |

## FTR

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| FTR-5.1 | Inventory Visitor sideline GG batteries | IR Tech (6.1-6.7) | 0 min |
| FTR-5.2 | Inventory Home sideline GG batteries | - | 0 min |
| FTR-5.3 | Inventory FTR Backpack (home games 1, 5 and 10) | - | 0 min |
| FTR-5.4 | Resolve and communicate any issues identified during the game | - | 0 min |
| FTR-5.5 | Secure IVR monitor using bungee cord | - | 0 min |
| FTR-5.6 | Pack up and secure IVR headsets and UNC tablet | - | 0 min |
| FTR-5.7 | Punch List any items that cannot be fixed before you leave via GMS.NFL.NET. This should only be the case if you need additional materials. | - | 0 min |
| FTR-5.8 | Complete your postgame report at GMS.NFL.NET within 24 hours of game end | - | 0 min |

## Hawk-Eye

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| Hawk-Eye-7.1 | Be on standby to assist with postgame for IVR and instant replay booths | Hawk-Eye (6.1-6.8) & Game Ended | 0 min |
| Hawk-Eye-7.2 | CONFIRM WITH SUPPORT BEFORE ANY POWERING DOWN, UNPATCHING OR PACKING | - | 0 min |
| Hawk-Eye-7.3 | Disconnect all BNC/coax from I/O patch panel | - | 0 min |
| Hawk-Eye-7.4 | Ensure TV has also disconnected from their end | - | 0 min |
| Hawk-Eye-7.5 | Coil up the NFL looms and pack into NFL Pelicase | - | 0 min |
| Hawk-Eye-7.6 | Return NFL Pelicase to designated storage location and share photo with Hawk-Eye Support WhatsApp | - | 0 min |
| Hawk-Eye-7.7 | Pack away instant replay booth into storage case (only if needed) | - | 0 min |
| Hawk-Eye-7.7a | Left Monitor & Right Monitor | - | 0 min |
| Hawk-Eye-7.7b | Center Monitor (4k Monitor) | - | 0 min |
| Hawk-Eye-7.8 | Pack away IVR booth into storage case (only if needed) | - | 0 min |
| Hawk-Eye-7.8a | Home AIO (All-in-One PC) & Visitor AIO (All-in-One PC) | - | 0 min |
| Hawk-Eye-7.8b | Home Spotter & Visitor Spotter | - | 0 min |
| Hawk-Eye-7.8c | UNC AIO (All-in-One PC) | - | 0 min |
| Hawk-Eye-7.8d | Move IVRS Storage Case back to designated location and share photo with Hawk-Eye Support WhatsApp | - | 0 min |
| Hawk-Eye-7.9 | IVR BOOTH: If IVR booth stays up, shut down the three AIOs | - | 0 min |
| Hawk-Eye-7.1 | IVR BOOTH: Secure away Xbox controllers | - | 0 min |
| Hawk-Eye-7.11 | IVR BOOTH: Ensure IVR booth is tidy, take a photo and post it in the Hawk-Eye WhatsApp | - | 0 min |
| Hawk-Eye-7.12 | INSTANT REPLAY: DO NOT SHUT DOWN VIEWERS (AMGC can do this remotely) OR IR RACK | - | 0 min |
| Hawk-Eye-7.13 | INSTANT REPLAY: Secure away Xbox controllers | - | 0 min |
| Hawk-Eye-7.14 | INSTANT REPLAY: Ensure Instant Replay booth is tidy, take a photo and post it in the Hawk-Eye WhatsApp | - | 0 min |
| Hawk-Eye-7.15 | HAWK-EYE RACK: LEAVE ALL CAPTURE SERVERS AND SWITCHES POWERED AND ONLINE | - | 0 min |
| Hawk-Eye-7.16 | HAWK-EYE RACK: Ensure Hawk-Eye rack is tidy (eg KVM slotted back into rack, doors closed) | - | 0 min |
| Hawk-Eye-7.17 | Complete Hawk-Eye Game Report within 2hr of conclusion of game | - | 0 min |
| Hawk-Eye-7.18 | Confirm with support all post game tasks completed | - | 0 min |
| Hawk-Eye-7.19 | Once wrapped up and heading off-site, post 'Hawk-Eye off-site' in the both the Football Technology and Hawk-Eye Support WhatsApp groups | - | 0 min |
| Hawk-Eye-7.2 | Clock out on the UKG App | - | 0 min |
| Hawk-Eye-8 | CONFIRM WITH HAWK-EYE SUPPORT BEFORE POWERING DOWN OR DISCONNECTING FLYAWAY RACK | Hawk-Eye (6.1-6.8) & Game Ended | 0 min |
| Hawk-Eye-8.1 | Disconnect BNC/coax looms plugged into patch panel | - | 0 min |
| Hawk-Eye-8.2 | Power down all flyaway rack capture servers | - | 0 min |
| Hawk-Eye-8.3 | Disconnect 2x opticalcon cables and pack neatly and securely inside flyaway rack door | - | 0 min |
| Hawk-Eye-8.4 | Disconnect power cables and neatly tuck inside flyaway rack | - | 0 min |
| Hawk-Eye-8.5 | Put doors back on flyaway rack | - | 0 min |
| Hawk-Eye-8.6 | Hand off Flyaway Rack back to the appropriate truck contact at the staging location that they specify or to loading dock in preparation for shipping -- CONFIRM WITH SUPPORT IF UNSURE | - | 0 min |
| Hawk-Eye-8.7 | TAKE A PHOTO OF FLYAWAY RACK AND POST TO HAWK-EYE WHATSAPP | - | 0 min |

## IR Tech

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IR Tech-6.1 | Park the ALL29 Camera | Game Ended | 0 min |

## IVRS

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| IVRS-6.1 | Collect all medical radios from teams. Home team has the option of holding onto their radios | O2O (5.1-5.4) & WiFi (7.1-7.6) & FTR (5.1-5.8) & C2P Home (6.1-6.10) & C2P Visitor (6.1-6.10) & SVS Home (10.1-10.13) & SVS Visitor (10.1-10.13) | 0 min |
| IVRS-6.2 | Collect Independent radios from UNC's, ATCs and AMP at designated pickup | - | 0 min |
| IVRS-6.4 | Pack up equipment and store in trunk | - | 0 min |
| IVRS-6.5 | Complete your postgame report at GMS.NFL.NET within 24 hours of game end | - | 0 min |
| IVRS-6.6 | Clock out of UKG when you leave the stadium | - | 0 min |

## O2O

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| O2O-5.1 | Confirm all belt packs are returned to the chargers | Game Ended | 0 min |

## SVS-Home

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Home-10.1 | Get Postgame Server Exports | Game Ended | 0 min |
| SVS-Home-10.2 | Gather SVS Logs if there were server issues (always in preseason) | - | 0 min |
| SVS-Home-10.3 | Confirm post-game Surface Pen Inventory, report missing items on GMS Game Report | - | 0 min |
| SVS-Home-10.4 | Shut Down StillShot Software | - | 0 min |
| SVS-Home-10.5 | Shut Down Surfaces using Shut Down Manger | - | 0 min |
| SVS-Home-10.6 | Shut Down Playview | - | 0 min |
| SVS-Home-10.7 | Shut Down StillShot Servers | - | 0 min |
| SVS-Home-10.8 | Ensure that Analyst is signed out of Excel on the Analytics Laptops | - | 0 min |
| SVS-Home-10.9 | Shutdown Analytics Laptops and store in SVS charging cart | - | 0 min |
| SVS-Home-10.1 | Put Surfaces back into Charging Carts and turn off carts | - | 0 min |
| SVS-Home-10.11 | Close-up DVSport StillShot Case | - | 0 min |
| SVS-Home-10.12 | Moisture Control | - | 0 min |
| SVS-Home-10.13 | Clock out of UKG when you leave the stadium | - | 0 min |

## SVS-Visitor

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| SVS-Visitor-10.1 | Get Postgame Server Exports | Game Ended | 0 min |
| SVS-Visitor-10.2 | Gather SVS Logs if there were server issues (always in preseason) | - | 0 min |
| SVS-Visitor-10.3 | Confirm post-game Surface Pen Inventory, report missing items on GMS Game Report | - | 0 min |
| SVS-Visitor-10.4 | Shut Down StillShot Software | - | 0 min |
| SVS-Visitor-10.5 | Shut Down Surfaces using Shut Down Manger | - | 0 min |
| SVS-Visitor-10.6 | Shut Down Playview | - | 0 min |
| SVS-Visitor-10.7 | Shut Down StillShot Servers | - | 0 min |
| SVS-Visitor-10.8 | Ensure that Analyst is signed out of Excel on the Analytics Laptops | - | 0 min |
| SVS-Visitor-10.9 | Shutdown Analytics Laptops and store in SVS charging cart | - | 0 min |
| SVS-Visitor-10.1 | Put Surfaces back into Charging Carts and turn off carts | - | 0 min |
| SVS-Visitor-10.11 | Close-up DVSport StillShot Case | - | 0 min |
| SVS-Visitor-10.12 | Moisture Control | - | 0 min |
| SVS-Visitor-10.13 | Clock out of UKG when you leave the stadium | - | 0 min |

## WiFi

| Task ID | Description | Dependencies | SLA |
| --- | --- | --- | --- |
| WiFi-7.1 | Return radio | Game Ended | 0 min |
| WiFi-7.2 | Secure IVR monitor using bungee cord | - | 0 min |
| WiFi-7.3 | Pack Up and secure IVR headsets and UNC tablet | - | 0 min |
| WiFi-7.4 | Breakdown Antennas and store | - | 0 min |
| WiFi-7.5 | Moisture control | - | 0 min |
| WiFi-7.6 | Complete your postgame report at GMS.NFL.NET within 24 hours of game end | - | 0 min |