SIPE ENGAGEMENT

ACCOUNTABILITY FRAMEWORK

NFL EVERGAME Phase II

IT Game Day Compliance & Readiness System

| Document ID: | SIPE-NFL-EVERGAME-ACCT-v1.0 |
| --- | --- |
| Classification: | NOVATE PROPRIETARY - CONFIDENTIAL |
| SIPE Tag: | TRANSFORMATION-CHALLENGE |
| Version: | 1.0 ¦ January 2026 |
| Status: | BINDING AGREEMENT |

Prepared by NOVATE Labs

Establishing Shared Accountability Standards for Engagement Success

TABLE OF CONTENTS

1. Engagement Overview & Parameters

2. Client Responsibilities (Binding Requirements)

3. NOVATE Responsibilities & Engagement Expectations

4. Issue Management Framework

5. Early Warning & Notification Triggers

6. Certification Sign-Off Framework

7. SIPE Documentation Standards

8. Framework Acknowledgment & Authorization

Appendix A: KPI Calculation Formulas

Appendix B: Escalation Contact Directory

1. ENGAGEMENT OVERVIEW & PARAMETERS

This Accountability Framework establishes the binding standards for the NFL EVERGAME Phase II engagement. As NOVATE's first full SIPE (Sentrais Innovation Playbook Engine) deployment, this framework sets the standard for all future engagements.

1.1 Engagement Summary

| Parameter | Value |
| --- | --- |
| Engagement Name | NFL EVERGAME Phase II - IT Game Day Compliance & Readiness |
| SIPE Classification | TRANSFORMATION-CHALLENGE |
| Duration | 24 weeks (March 3 - August 15, 2026) |
| Methodology | NIN 5D Framework (Discover → Deploy) |
| Target Milestone | 2026 NFL Preseason Readiness |
| Critical Churn Zones | D2 DIAGNOSE & D3 DESIGN (Weeks 4-12) |
| GDA Go-Live Target (Base Scope) | June 30, 2026 (pending contract execution and NFL dependencies) |

1.2 Key Deliverables

| # | Deliverable | Phase | Target |
| --- | --- | --- | --- |
| D1 | Centralized System of Record | D4-D5 | Week 20 |
| D2 | Game Day Dashboard | D4-D5 | Week 20 |
| D3 | Stadium Certification (To-Be) - Design and Prototype Only (No Go-Live) | D1-D3 | Within Phase II |
| D4 | GDA Certification Process (To-Be) - Base Scope | D3 | Week 12 |
| D5 | 2026 GDA Checklist Playbook | D3-D4 | Week 16 |
| D6 | Evidence Capture System | D4-D5 | Week 20 |
| D7 | IT Master Calendar | D4-D5 | Week 20 |
| D8 | Enhanced GDA Tools | D5 | Week 22 |
| D9 | IT Events Readiness (To-Be) - Design and Prototype Only (No Go-Live) | D1-D3 | Within Phase II |

1.3 Scope and Commercial Guardrails

10. Any client-driven checklist changes outside the agreed change control process, especially during live operations.

9. New dashboards, new administrative consoles, additional roles or permissions models beyond the agreed baseline, or any cross-system write-back logic not explicitly contracted.

8. IT Events Readiness production build, integrations, UAT, or go-live.

7. Stadium Certification production build, integrations, UAT, or go-live for the 2026 season. Hall of Fame and international stadium workflows are explicitly out of scope.

Out of Scope (Requires Change Order)

6. Stadium Certification and IT Events Readiness will be addressed through workshops, requirements forensics, and a simulator-level prototype only. This work produces a To-Be workflow, a prototype walkthrough, and an implementation backlog with estimated effort. It does not include production build, integrations, UAT, or go-live in Phase II.

Good-Faith Support (NIN 3Ds Only: Discover, Diagnose, Design)

5. Training, UAT support, and go-live for the GDA module by June 30, 2026, contingent on contract execution and NFL-provided dependencies.

4. Limited integrations and data exchanges explicitly enumerated in the contract or Appendix (no implied integrations).

3. Security hardening and access controls for NFL deployment, including configuration controls to protect playbooks and core logic.

2. EVERGAME as the system of record for the GDA readiness program (replacing spreadsheets as the authoritative operational workspace).

1. GDA Readiness and Certification implementation (production) including 2026 GDA checklist playbooks, evidence capture workflow, and game day dashboards.

Base Contract Scope (In Scope)

This engagement is structured as a dual-track program: (1) a contracted build and deployment for the GDA Readiness and Certification capability, and (2) good-faith NIN workshops (Discover, Diagnose, Design) for adjacent domains to establish an authoritative source of truth and a priced implementation backlog. To prevent scope creep and protect both parties, the boundaries below are binding for Phase II unless and until changed via formal change order.

2. CLIENT RESPONSIBILITIES (Binding Requirements)

⚠ CLIENT ACKNOWLEDGMENT: Failure to meet the responsibilities outlined in this section may result in timeline delays, increased costs, or scope reduction. NOVATE will document all client-attributable delays in the Evidence Ledger.

2.1 Executive Sponsorship Requirements

- Designate VP-level or above Executive Sponsor with decision-making authority

- Attend monthly Executive Steering Committee meetings (minimum 80% attendance) and bi-weekly Technical Advisory Committee meetings as required for decisions.

- Provide stage gate approvals within 3 business days of submission (or formally reject with rationale and next-step guidance).

- Respond to escalation requests within 24 hours

- Maintain budget authority for approved scope and contingency

2.1.1 Governance Bodies and Cadence

The engagement will be governed through three layers to ensure decision velocity, source-of-truth alignment, and change control.

| Body | Purpose | Cadence | Decision Rights |
| --- | --- | --- | --- |
| Executive Steering Committee (NFL approval triad + NOVATE steering) | Approve scope, funding, go-live, and major changes. Resolve escalations. | Monthly (3rd week, Thu, 1 hour) plus ad hoc as needed | Major scope and budget changes; go-live authorization |
| Technical Advisory Committee (NFL workstream leads + NOVATE leads) | Validate source of truth, requirements, workflow decisions, and change requests before implementation. | Bi-weekly (60-90 min) | Process decisions, minor scope changes within baseline |
| Technical Delivery Sync (NOVATE build team + NFL SMEs as needed) | Execute delivery, remove blockers, confirm technical assumptions. | 2x per week | Technical decisions within agreed architecture; no scope changes |

2.2 Stakeholder Availability Requirements

| Stakeholder Group | Availability | Response SLA | Phases |
| --- | --- | --- | --- |
| NFL IT Leadership | 4 hours/week | 24 hours | All (D1-D5) |
| Technical SMEs | 8 hours/week (D2-D3) | 48 hours | D2, D3, D4 |
| GDA Representatives | 5-person pilot team | 72 hours | D1, D3, D4 |
| Stadium IT Leads | 3 pilot stadiums | 72 hours | D3, D4 |
| Vendor Partners | Named contacts | 1 week | D2, D3, D4 |

2.3 Documentation & Data Access

| Document Category | Required By | Priority | Status |
| --- | --- | --- | --- |
| Strategic roadmaps & board presentations | Week 1 | CRITICAL | ☐ |
| Technical architecture & system diagrams | Week 2 | CRITICAL | ☐ |
| Current operational processes & workflows | Week 2 | HIGH | ☐ |
| Historical performance data & KPIs | Week 3 | HIGH | ☐ |
| Vendor contracts & SLAs | Week 3 | MEDIUM | ☐ |
| Stadium access for pilot testing | Week 12 | CRITICAL | ☐ |

2.4 Decision-Making & Approvals

| Decision Type | Approver | SLA | Escalation |
| --- | --- | --- | --- |
| Stage Gate Progression | NFL Executive Sponsor (or designee) + NOVATE Program Lead | 3 business days | Escalate to Executive Steering |
| Scope Changes (Minor) | Technical Advisory Committee (TAC) approval | 2 business days | Executive Steering |
| Scope Changes (Major) | Executive Steering Committee approval (NFL approval triad) | 5 business days | N/A |
| Design Approvals | IT Leadership + SMEs | 5 days | Exec Sponsor |
| UAT Sign-off (GDA Base Scope) | NFL GDA Lead + NOVATE Program Lead | 3 business days | NFL IT Director |
| Go-Live Authorization (GDA Base Scope) | NFL Executive Sponsor + NFL IT Owner | 2 business days | NFL CIO |

3. NOVATE RESPONSIBILITIES & ENGAGEMENT EXPECTATIONS

3.1 Delivery Commitments

- 100% adherence to SIPE methodology and stage gate requirements

- Evidence Ledger entries within 24 hours of all significant events

- All deliverables reviewed through internal QA before client submission

- Milestone adherence within ±5 business days of planned dates

- Resource continuity - named team members for duration of engagement

- Comprehensive knowledge transfer and documentation at engagement close

3.1.1 Named Team and Role Accountability

NOVATE will staff the engagement with named leads to ensure clear ownership and minimize delivery risk. The NFL will designate named owners for each workstream and for the GDA pilot group.

| Role | Owner | Primary Accountability |
| --- | --- | --- |
| NOVATE Steering Committee Member | Tye Hayes (CEO) | Executive oversight, IP protection, executive escalations |
| NOVATE Program Lead (Client-facing) | Erin Greene | Engagement leadership, TAC facilitation, scope control and stage gates |
| NOVATE Technical Lead | Kirby | Technical architecture, security controls, build quality, integration approach |
| NOVATE PMO | Asia Lewis | Artifact governance, evidence ledger, RAID log, status reporting |
| NOVATE Executive Oversight | Knox Phillips | Commercial and legal alignment, contract posture, executive communications |
| NFL Executive Sponsor | Gary Brantley (or designee) | Executive decisions, go-live authorization path, escalations |
| NFL PMO / Program Host | Sandra Manigault (Primary) / Victoria Donten (Alt) | Program coordination, meeting facilitation, documentation routing |
| NFL Workstream Leads (TAC) | NFL IT leads per domain | Requirements ownership and approvals within TAC |

3.2 Communication Standards

| Communication Type | Frequency | Format | Recipients |
| --- | --- | --- | --- |
| Weekly Status Report | Every Friday 3pm ET | PDF + Dashboard | Project Team + Leads |
| Technical Sync | 2x per week | Meeting + Notes | Technical SMEs |
| Steering Committee | Bi-weekly | Executive Summary | Leadership |
| Stage Gate Review | Per phase | Gate Package | All Stakeholders |
| Risk/Issue Alert | Within 4 hours | Alert + Action Plan | Relevant Owners |
| Monthly Executive Brief | Monthly | Presentation | Exec Sponsor + CIO |

3.3 What the Client Can Expect from NOVATE

- TRANSPARENCY: Real-time visibility into project status via Sentrais dashboard

- PROACTIVE COMMUNICATION: Early warning of risks before they become issues

- EVIDENCE-BASED DECISIONS: All recommendations backed by documented analysis

- SHARED ACCOUNTABILITY: Clear ownership of actions on both sides

- FORENSIC RIGOR: Audit-ready documentation at every stage

- EXPERTISE: Deep methodology knowledge and industry best practices

- PARTNERSHIP: Collaborative approach focused on mutual success

4. ISSUE MANAGEMENT FRAMEWORK

4.1 Issue Classification Matrix

| Severity | Definition | Initial Response | Resolution Plan |
| --- | --- | --- | --- |
| CRITICAL | Blocks engagement entirely or threatens overall success/timeline | 2 hours | 24 hours |
| HIGH | Significant timeline or quality impact requiring immediate attention | 4 hours | 48 hours |
| MEDIUM | Notable impact but workarounds exist; requires near-term resolution | 24 hours | 1 week |
| LOW | Minor inconvenience with minimal impact on deliverables | 1 week | Next phase |

4.2 Issue Categories & Owners

| Category | Description | Primary Owner |
| --- | --- | --- |
| Technical | System, integration, or infrastructure problems | NOVATE Technical Lead |
| Resource | Staffing, availability, or capacity issues | Joint PM Team |
| Scope | Requirements changes or scope creep | NOVATE Engagement Lead |
| Timeline | Schedule delays or milestone risks | NOVATE PM |
| Vendor | Third-party dependencies or blockers | NFL IT Lead |
| Quality | Deliverable standards or defects | NOVATE QA Lead |
| Communication | Information gaps or misalignment | Joint PM Team |

4.3 Escalation Path

| Level | NOVATE | NFL | Trigger |
| --- | --- | --- | --- |
| L1 | Project Manager | IT Project Lead | Initial identification |
| L2 | Engagement Lead | IT Director | Unresolved >48hr or HIGH severity |
| L3 | Program Director | VP IT | Unresolved >5 days or >1 week impact |
| L4 | CEO (Tye) | Executive Sponsor | CRITICAL or engagement at risk |

4.4 Issue Resolution Process

All issues follow the 8-step resolution process:

- Step 1 - IDENTIFY: Issue detected and initial assessment completed

- Step 2 - CLASSIFY: Severity and category assigned per matrix

- Step 3 - ASSIGN: Primary owner designated based on category

- Step 4 - ANALYZE: Root cause analysis conducted

- Step 5 - PLAN: Resolution approach documented with timeline

- Step 6 - EXECUTE: Resolution actions implemented

- Step 7 - VERIFY: Resolution validated by affected parties

- Step 8 - CLOSE: Issue closed with lessons learned documented

All issues logged in Evidence Ledger within 4 hours with unique ID: ISS-NFL-[PHASE]-###

5. EARLY WARNING & NOTIFICATION TRIGGERS

⚠ CRITICAL CHURN ZONE: Per SIPE methodology, 60% of engagement delays occur during D2 DIAGNOSE and D3 DESIGN phases (Weeks 4-12). Enhanced monitoring is mandatory during this period.

5.1 Churn Prevention Indicators (D2-D3 Critical Phases)

| Indicator | Alert Threshold | Escalate Threshold | Owner |
| --- | --- | --- | --- |
| Requirements Ambiguity Score (RAS) | >20 | >40 | Engagement Lead |
| Stakeholder Alignment Index (SAI) | <85% | <70% | Program Director |
| Scope Stability Score (SSS) | <85 | <70 | Steering Committee |
| Decision Bottleneck Index (DBI) | >3 delays | >5 delays | Exec Sponsor |
| Technical Feasibility Confidence | <80% | <65% | Technical Leads |
| Timeline Compression Rate | >15% | >25% | Program Director |
| Resource Allocation Gap | >7 days unfilled | >14 days | Joint PM Team |
| Client Engagement Decline | >20% drop | >35% drop | Exec Sponsor |

5.2 General Engagement Triggers

| Trigger Condition | Detection | Action |
| --- | --- | --- |
| Stakeholder meeting attendance drops >20% | Automated | PM escalation to Lead |
| Document request overdue >5 business days | Automated | Direct follow-up |
| 3+ conflicting stakeholder inputs identified | Manual | Alignment workshop |
| >2 scope expansion requests in single week | Manual | Change board review |
| Technical blocker identified with no workaround | Manual | Immediate SME session |
| Stage Gate criteria at risk (5 days out) | Automated | Gate readiness review |
| Budget variance exceeds 10% | Automated | Financial review |
| Quality gate failure | Manual | Rework + root cause |

5.3 Notification Protocol

| Level | Channel | Recipients | Response Required |
| --- | --- | --- | --- |
| INFO | Dashboard only | Project Team | Awareness only |
| WATCH | Weekly report highlight | Project Leads | Monitor and plan |
| ALERT | Email + Dashboard flag | Leads + Directors | Action within 48 hours |
| CRITICAL | Email + Phone + Meeting | Executives + Steering | Immediate action required |

5.4 Automated Intervention Protocols

- 1 indicator in ALERT → Engagement Lead notified, monitoring frequency increased, RCA within 24hr

- 2+ indicators in ALERT → Executive checkpoint auto-scheduled, mitigation plan within 48hr

- Any indicator in ESCALATE → Client escalation with formal mitigation plan, Steering review

- Multiple ESCALATE → Formal reset workshop or pause recommendation, executive intervention

6. CERTIFICATION SIGN-OFF FRAMEWORK

Formal certification is required for all phase transitions. No phase advancement occurs without documented evidence meeting all criteria and executive sign-off. All certifications logged in Evidence Ledger.

6.1 Stage Gate 1: D1 DISCOVER → D2 DIAGNOSE

| Exit Criterion | Threshold | Status |
| --- | --- | --- |
| Problem statement validated by stakeholders | 3+ executive sign-offs | ☐ |
| 360 Model data collection complete | 100% all 6 dimensions | ☐ |
| KPI baseline established | All success metrics defined | ☐ |
| Sentrais project initialized | 100% setup complete | ☐ |
| Stakeholder Engagement Index (SEI) | ≥75 | ☐ |
| Evidence Quality Rating | ≥80 | ☐ |

Required Signatures:

| NOVATE Engagement Lead | NOVATE Program Director | NFL IT Project Lead | NFL Executive Sponsor |
| --- | --- | --- | --- |

6.2 Stage Gate 2: D2 DIAGNOSE → D3 DESIGN (CRITICAL GATE)

⚠ CRITICAL CHURN ZONE: This gate represents the highest risk point in the engagement. Enhanced scrutiny required.

| Exit Criterion | Threshold | Status |
| --- | --- | --- |
| Workflow forensics completed | 95%+ accuracy | ☐ |
| Risk register complete with mitigations | All HIGH risks addressed | ☐ |
| Gap analysis documented | 100% coverage | ☐ |
| Scope Stability Score (SSS) | ≥85 | ☐ |
| Requirements Ambiguity Score (RAS) | ≤20 | ☐ |
| Executive checkpoint documented | Completed | ☐ |

Required Signatures:

| NOVATE Engagement Lead | NOVATE Program Director | NFL IT Director | NFL Executive Sponsor |
| --- | --- | --- | --- |

6.3 Stage Gate 3: D3 DESIGN → D4 DEVELOP

| Exit Criterion | Threshold | Status |
| --- | --- | --- |
| Solution concepts evaluated | 3+ concepts scored | ☐ |
| Technical Feasibility Confidence | ≥80% | ☐ |
| Innovation Coefficient | ≥60% | ☐ |
| Stakeholder Alignment Index (SAI) | ≥85% | ☐ |
| Resource plan validated | 100% committed | ☐ |
| Design approvals complete | All sign-offs obtained | ☐ |

Required Signatures:

| NOVATE Engagement Lead | NOVATE Technical Lead | NFL IT Director | NFL Executive Sponsor |
| --- | --- | --- | --- |

6.4 Stage Gate 4: D4 DEVELOP → D5 DEPLOY

| Exit Criterion | Threshold | Status |
| --- | --- | --- |
| Pilot stadiums executed | 3 stadiums complete | ☐ |
| Stage Gate Pass Rate | ≥70% | ☐ |
| Client Satisfaction Score | ≥80 | ☐ |
| Critical defects | <5% | ☐ |
| Go/No-Go decision documented | Evidence-based | ☐ |
| UAT sign-off complete | All users approved | ☐ |

Required Signatures:

| NOVATE Engagement Lead | NOVATE QA Lead | NFL IT Director | NFL GDA Lead |
| --- | --- | --- | --- |

6.5 Stage Gate 5: D5 DEPLOY → OPERATIONAL (Final Gate)

| Exit Criterion | Threshold | Status |
| --- | --- | --- |
| Integration testing complete | <5% critical defects | ☐ |
| User adoption rate | ≥60% within 30 days | ☐ |
| Operational runbooks complete | 100% documented | ☐ |
| Knowledge transfer validated | All teams certified | ☐ |
| Time-to-Value | Within ±15% projection | ☐ |
| Preseason readiness confirmed | Systems operational | ☐ |

Required Signatures:

| NOVATE Program Director | NOVATE CEO (Tye) | NFL VP IT | NFL Executive Sponsor |
| --- | --- | --- | --- |

7. SIPE DOCUMENTATION STANDARDS

As NOVATE's first full SIPE deployment, this engagement establishes standardized documentation practices for all future engagements.

7.1 Document Identification Standards

| Document Type | ID Format | Example |
| --- | --- | --- |
| Core Documents | SIPE-[CLIENT]-[PROJECT]-[TYPE]-v[X.Y] | SIPE-NFL-EVERGAME-PROPOSAL-v1.0 |
| Issues | ISS-[CLIENT]-[PHASE]-[###] | ISS-NFL-D2-001 |
| Change Requests | CR-[CLIENT]-[###] | CR-NFL-015 |
| Evidence Entries | [TYPE]-[CLIENT]-[PHASE]-[###] | INT-NFL-D1-003 (Interview) |
| Document Requests | DRF-[CLIENT]-[PHASE]-[###] | DRF-NFL-D1-007 |
| Decision Records | DEC-[CLIENT]-[###] | DEC-NFL-042 |

7.2 Evidence Ledger Entry Requirements

All Evidence Ledger entries must be submitted within 24 hours and include:

- Entry ID (per format above)

- Entry Type: INT (Interview), DOC (Document), DEC (Decision), OBS (Observation), ISS (Issue), MTG (Meeting)

- 360 Dimension: Strategic, Operational, Technical, Cultural, Financial, Ecosystem

- Date/Time (ISO 8601 format)

- Author and Source

- Summary (≤100 words)

- Key Findings (bullet points)

- Attachments (file references)

- Follow-Up Items (action items with owners and dates)

7.3 Version Control Standards

| Version Type | Increment | Description | Approval |
| --- | --- | --- | --- |
| MAJOR | X.0 | Breaking changes, methodology shifts, architecture redesign | Program Director |
| MINOR | X.Y | Feature additions, new sections, enhanced capabilities | Engagement Lead |
| PATCH | X.Y.Z | Bug fixes, clarifications, typo corrections | Document Owner |

7.4 Classification Levels

| Level | Description | Access |
| --- | --- | --- |
| RESTRICTED | Highly sensitive: core IP, competitive intelligence, security | Named individuals only |
| CONFIDENTIAL | Client-specific: engagement details, deliverables, contracts | Client + NOVATE team |
| INTERNAL | NOVATE operational: playbooks, processes, templates | NOVATE employees |
| PUBLIC | Marketing materials, published case studies | Unrestricted |

8. FRAMEWORK ACKNOWLEDGMENT & AUTHORIZATION

8.1 Summary of Commitments

By signing this framework, both parties acknowledge and commit to:

NFL Commitments:

- Executive sponsor availability and decision-making per SLAs

- Stakeholder participation as specified in Section 2

- Timely provision of documentation and data access

- Prompt response to escalations and issue resolution

- Stage Gate certification participation

NOVATE Commitments:

- 100% SIPE methodology adherence

- Communication standards per Section 3

- Proactive risk identification and early warning notification

- Evidence-based deliverables with forensic documentation

- Milestone adherence within stated tolerances

8.2 Framework Authorization

This SIPE Engagement Accountability Framework is hereby acknowledged and accepted by both parties. This document establishes binding accountability standards for the NFL EVERGAME Phase II engagement.

| FOR NOVATE LABS: | FOR NFL: |
| --- | --- |
| ________________________________ Tye, CEO Date: ____________________ | ________________________________ Executive Sponsor, VP IT Date: ____________________ |
| ________________________________ Program Director Date: ____________________ | ________________________________ IT Director, Game Day Operations Date: ____________________ |

APPENDIX A: KPI CALCULATION FORMULAS

A.1 Stakeholder Engagement Index (SEI)

SEI = (Meeting Attendance Rate × 0.4) + (Response Time Score × 0.3) + (Decision Velocity Score × 0.3)

- Meeting Attendance Rate = (Meetings Attended ÷ Meetings Invited) × 100

- Response Time Score = 100 - (Avg Response Hours ÷ 48 × 100)

- Decision Velocity Score = (Decisions On Time ÷ Total Decisions) × 100

A.2 Scope Stability Score (SSS)

SSS = 100 - Scope Change Impact

- Scope Change Impact = Σ(Change Magnitude × Change Frequency)

- Change Magnitude: MINOR (1), MODERATE (3), MAJOR (5)

A.3 Requirements Ambiguity Score (RAS)

RAS = (Unclear Requirements ÷ Total Requirements) × 100 + Conflict Penalty

- Conflict Penalty = Number of conflicting requirements × 5

A.4 Churn Risk Score (CRS)

CRS = (RAS × 0.3) + (Alignment Gap × 0.25) + (Feasibility Concern × 0.25) + (Resource Variance × 0.2)

- Low Risk: CRS < 30

- Medium Risk: 30 ≤ CRS < 60

- High Risk: CRS ≥ 60 (Immediate intervention required)

A.5 Evidence Quality Rating

Evidence Quality = Dimension Coverage (25) + Source Validation (25) + Timeliness (25) + Tagging Accuracy (25)

APPENDIX B: ESCALATION CONTACT DIRECTORY

B.1 NOVATE Escalation Contacts

| Role | Name | Email |
| --- | --- | --- |
| CEO | Tye | [To be completed] |
| Program Director | [To be assigned] | [To be completed] |
| Engagement Lead | [To be assigned] | [To be completed] |
| Technical Lead | [To be assigned] | [To be completed] |
| Project Manager | [To be assigned] | [To be completed] |

B.2 NFL Escalation Contacts

| Role | Name | Email |
| --- | --- | --- |
| Executive Sponsor | [To be assigned] | [To be completed] |
| VP IT | [To be assigned] | [To be completed] |
| IT Director | [To be assigned] | [To be completed] |
| IT Project Lead | [To be assigned] | [To be completed] |
| GDA Lead | [To be assigned] | [To be completed] |

DOCUMENT CONTROL

| Document ID: | SIPE-NFL-EVERGAME-ACCT-v1.0 |
| --- | --- |
| Version: | 1.0 |
| Release Date: | January 2026 |
| Classification: | NOVATE PROPRIETARY - CONFIDENTIAL |
| SIPE Reference: | SIPE Core Architecture v1.0, Sections 2-4, 8-9 |
| Next Review: | Post-engagement or upon SIPE v1.1 release |

END OF DOCUMENT