## Slide 1
NFL EVERGAME Phase II
Implementation Timeline & Workstream Mapping
GDA Lifecycle • Stadium Certification Lifecycle • IT Events Lifecycle
March 3 – August 15, 2026 (24 Weeks)

## Slide 2
Workstream Delivery Model
Three parallel lifecycles with distinct delivery commitments
GDA Readiness & Certification Lifecycle
PRODUCTION DELIVERY
Full production implementation including playbooks, evidence workflows, dashboards, calendar integration, training, UAT, and go-live support. Go-Live: June 30, 2026
Stadium Certification Lifecycle
DESIGN + PROTOTYPE
Good-faith deliverables: Current-state review, To-Be workflow design, simulator-level prototype, implementation roadmap with effort estimates. Production build requires change order.
IT Events Readiness Lifecycle
DESIGN + PROTOTYPE
Good-faith deliverables: Current-state review, To-Be workflow design, simulator-level prototype, implementation roadmap with effort estimates. Production build requires change order.

## Slide 3
Implementation Phases Overview
Phase 1: Discovery & Alignment
Weeks 1-3
• Kick-off and stakeholder alignment
• Requirements validation and source of truth confirmation
• Current-state documentation (all workstreams)
• Dependency mapping and risk assessment
• Stage Gate 1: Scope & Requirements Sign-Off
Phase 2: Design & Validation
Weeks 4-12
• GDA final design and workflow configuration
• Stadium Certification To-Be workflow design
• IT Events To-Be workflow design
• Technical architecture validation
• Stage Gate 2: Design Approval & Build Authorization
Phase 3: Build & Configuration
Weeks 13-20
• GDA production system build
• Stadium Certification simulator prototype
• IT Events simulator prototype
• Integration configuration and testing
• Stage Gate 3: Build Complete & UAT Readiness
Phase 4: UAT & Readiness
Weeks 21-23
• GDA user acceptance testing
• Training delivery (GDA users)
• Documentation finalization
• Go-live readiness review
• Stage Gate 4: Go-Live Authorization
Phase 5: Go-Live & Stabilization
Week 24
• GDA production go-live (June 30, 2026)
• Hypercare support and monitoring
• Issue triage and resolution
• Stadium Cert & IT Events roadmap delivery
• Phase II closure and Phase III planning

## Slide 4
GDA Readiness & Certification Lifecycle
PRODUCTION
Phase | Weeks | Key Activities | Deliverables | Gate Criteria
Discovery & Alignment | 1-3 | • Stakeholder interviews • GDA checklist review • WhatsApp workflow analysis • Dependency mapping | • Requirements document • Current-state process map • Risk register • Implementation plan | ✓ Requirements signed ✓ SMEs assigned ✓ Dependencies mapped
Design & Validation | 4-12 | • Playbook configuration • Evidence workflow design • Dashboard wireframes • Calendar integration spec | • Final GDA design • Workflow diagrams • Dashboard mockups • Integration architecture | ✓ Design approved ✓ Tech stack validated ✓ Build plan confirmed
Build & Configuration | 13-20 | • System build • Playbook creation • Dashboard development • Calendar integration • Security hardening | • Configured system • 2026 GDA playbooks • Operational dashboards • IT Master Calendar • Security documentation | ✓ All features built ✓ Integration tested ✓ Security reviewed
UAT & Readiness | 21-23 | • User acceptance testing • Training delivery • Documentation • Go-live preparation | • UAT sign-off • Training materials • User guides • Runbooks • Go-live checklist | ✓ UAT passed ✓ Users trained ✓ Docs complete
Go-Live | 24 | • Production cutover • Hypercare monitoring • Issue resolution • Process optimization | • Live GDA system • Hypercare logs • Lessons learned • Optimization backlog | ✓ Go-live successful ✓ Spreadsheets retired ✓ Support stabilized
Phase | Weeks | Key Activities | Deliverables | Gate Criteria

## Slide 5
Stadium Certification Lifecycle
DESIGN + PROTOTYPE
Phase | Weeks | Key Activities | Deliverables | Status
Discovery | 1-3 | • Current certification process review • Stakeholder interviews • Pain point identification • Requirements gathering | • Current-state documentation • Requirements matrix • Stakeholder feedback log | ✓ Design scope (No production build)
Design | 4-12 | • To-Be workflow design • Certification criteria mapping • Approval routing design • Dashboard concept • Integration touchpoints | • To-Be process flows • Certification playbooks (design) • Dashboard wireframes • Integration requirements doc | ✓ Design approved (Production build requires change order)
Prototype | 13-20 | • Simulator-level prototype build • Workflow demonstration • Stakeholder validation • Technical feasibility proof | • Interactive simulator • Demo environment • Validation feedback • Technical architecture | ✓ Prototype demo (Not production- ready)
Roadmap | 21-24 | • Production implementation plan • Effort estimation • Resource requirements • Cost modeling • Phase III proposal | • Implementation roadmap • Effort estimate (hours/cost) • Phase III SOW • Change order template | ✓ Roadmap delivered (Phase III planning input)
Phase | Weeks | Key Activities | Deliverables | Status
⚠ Stadium Certification Scope Boundary
Phase II Commitment: Design + prototype to validate feasibility and inform Phase III planning
Out of Scope: Production build, go-live, training, or operational support. These activities require a change order and are proposed for Phase III (post-August 2026).

## Slide 6
IT Events Readiness Lifecycle
DESIGN + PROTOTYPE
Phase | Weeks | Key Activities | Deliverables | Status
Discovery | 1-3 | • IT Events inventory • Current planning process review • Stakeholder needs assessment • Integration dependencies | • Event categories taxonomy • Current-state workflows • Requirements catalog • Integration map | ✓ Design scope (No production build)
Design | 4-12 | • To-Be event lifecycle design • Planning workflow configuration • Readiness criteria framework • Dashboard requirements • Notification design | • Event lifecycle flows • Planning playbooks (design) • Readiness checklists • Dashboard wireframes • Communication templates | ✓ Design approved (Production build requires change order)
Prototype | 13-20 | • Simulator-level prototype • Multi-event scenario testing • Workflow validation • Stakeholder demos • Technical proof-of-concept | • Interactive simulator • Event scenario library • Demo environment • Validation results • Technical design doc | ✓ Prototype demo (Not production- ready)
Roadmap | 21-24 | • Production build planning • Resource and timeline estimates • Phased rollout strategy • Cost analysis • Phase III proposal | • Implementation roadmap • Build estimate (hours/cost) • Rollout plan • Phase III SOW • Change order template | ✓ Roadmap delivered (Phase III planning input)
Phase | Weeks | Key Activities | Deliverables | Status
⚠ IT Events Readiness Scope Boundary
Phase II Commitment: Design + prototype to validate approach and inform Phase III planning
Out of Scope: Production build, event-specific configurations, go-live, training, or operational support. These activities require a change order and are proposed for Phase III (post-August 2026).

## Slide 7
Integrated Workstream Timeline
All three lifecycles running in parallel with distinct delivery commitments
Weeks 1-3
Discovery
Weeks 4-12
Design
Weeks 13-20
Build
Weeks 21-23
UAT
Weeks 24
Go-Live
GDA
PRODUCTION GO-LIVE →
Stadium
DESIGN + PROTOTYPE →
Roadmap
IT Events
DESIGN + PROTOTYPE →
Roadmap
Legend:
= Production delivery (contractual commitment)
= Roadmap/planning (good-faith deliverable, no production build)

## Slide 8
Stage Gates & Governance Checkpoints
Critical decision points for all workstreams with go/no-go criteria
Stage Gate 1
End of Week 3
Gate Criteria:
• Requirements signed off by NFL and NOVATE
• All workstream scopes clearly defined and documented
• SMEs assigned and available
• Dependencies mapped with mitigation plans
• Risk register established
Decision:
Proceed to Design or escalate scope issues
Stage Gate 2
End of Week 12
Gate Criteria:
• GDA final design approved by Technical Advisory Committee
• Stadium Cert & IT Events To-Be designs validated
• Technical architecture reviewed and approved
• Build plan confirmed with resource allocation
• Integration requirements documented
Decision:
Authorize GDA build + prototype work
Stage Gate 3
End of Week 20
Gate Criteria:
• GDA system build complete and tested
• Stadium Cert & IT Events prototypes functional
• Integration testing passed
• UAT environment ready
• Training materials prepared
Decision:
Proceed to UAT or remediate build issues
Stage Gate 4
End of Week 23
Gate Criteria:
• GDA UAT completed with sign-off
• All critical defects resolved
• Users trained and certified
• Go-live runbook approved
• Hypercare plan in place
Decision:
Authorize GDA production go-live

## Slide 9
Cross-Workstream Dependencies & Risks
Key Dependencies
NFL Inputs
2026 GDA checklists, stadium certification criteria, IT events calendar
Impact: Delays in delivery affect all three workstreams
Mitigation: Establish SLA for document delivery (Week 2)
SME Availability
Subject matter experts for requirements, validation, UAT
Impact: Bottlenecks in design and testing phases
Mitigation: Named SMEs assigned at kickoff with % allocation
Technical Architecture
Shared infrastructure, integration points, security model
Impact: All workstreams depend on common tech stack
Mitigation: Architecture locked at Stage Gate 2
Critical Risks
Scope Creep (Stadium/IT Events)
HIGH
Impact: Timeline delay, budget overrun
Mitigation: Strict change control, weekly governance review
GDA Go-Live Delay
MEDIUM
Impact: Missed 2026 season deadline
Mitigation: 2-week buffer in UAT phase, hypercare team ready
Stakeholder Misalignment
MEDIUM
Impact: Rework in design/build phases
Mitigation: Stage gates with sign-off, bi-weekly TAC meetings

## Slide 10
Phase III Transition Planning
Stadium Certification and IT Events production implementation (Post-August 2026)
Phase II Deliverables (Week 24)
Stadium Certification:
• Interactive simulator/prototype
• To-Be workflow documentation
• Implementation roadmap with effort estimates
• Phase III SOW and change order template
IT Events Readiness:
• Interactive simulator/prototype
• Event lifecycle design documentation
• Implementation roadmap with effort estimates
• Phase III SOW and change order template
Phase III Proposed Scope
Stadium Certification Production:
• Full system build based on approved design
• Stadium-specific configurations
• Approval workflow implementation
• Training and go-live support
IT Events Production:
• Full system build based on approved design
• Multi-event lifecycle configuration
• Integration with GDA and Stadium modules
• Training and go-live support
Phase III Go/No-Go Decision Framework
GDA Success
Phase II GDA go-live successful with stable operations
Prototype Validation
Stadium Cert & IT Events simulators validated by stakeholders
Business Case
ROI and business value confirmed for production build
Resource Availability
NFL and NOVATE resources committed for Phase III
Budget Approval
Phase III funding secured based on effort estimates

## Slide 11
Implementation Readiness
Three Lifecycles • One Integrated Timeline
GDA Production Delivery • Stadium Cert Design & Prototype • IT Events Design & Prototype
March 3 – August 15, 2026